**Transnational Project Meeting**

Host: Nordre Skole, Viborg - Denmark

Dates: November 4th – 8th 2017

**AGENDA**

**1. WELCOME TO ALL!**

* Wales: Paul, Sioned
* Italy: Luca, Alessandra, Maria
* Germany: Annie, Kathrin
* Iceland: Erla, Pollý
* Spain: Carolina, Carmen

**2. REVIEWING THE CURRENT PROJECT ACTIVITIES:**

* A20: Guest teachers. Deadline: end of 2017.
* A21: Cultural visits. Deadline: Feb-March 2018
* A22. Visiting Creative companies. Deadline: end of 2017.
* A28: Famous artist. Deadline: September 2017. Upload in the wikispaces
* A15: Sixty Inspiring Ideas. Small changes to be made by Magga. Deadline: October 2017. Please send a new link to wikispace in WORD format. Magga has created a new page where to add it.
* A25: Birthday Calendar. Deadline: June 2017. (Drawings from Wales are missing)
* A30: From My window. Postcards/photos/films. Shared through e-twinning/take along to DK. Deadline: October 2017
* A32 Booklet of the LA in Blücherschule. Deadline: TPM in Denmark.
* A33: A fifty word play. WALES to send a basic story in English to all. Deadline: Beg.of September. ALL COUNTRIES to make a video with the story in their own language with English subtitles. Shared through e-twinning/wikispaces. Deadline: Christmas 2017
* A34: Exciting English. Send 5 ideas/country to Elisa (use WORD please!) by October 15th. Elisa will collate a booklet. The format has been uploaded to wikispaces.
* A36: Quiz in Basic skills. Spain presents the idea.

**3. PLANNING FORWARD**

* A37 Good Deeds Competition

- Wales to coordinate; how to be shared? Deadline: Christmas 2017

* A38 A Day in My Life

- Video diaries about our lives

- Spain to coordinate – how to share? Deadline: LA in Italy

* A39 This is How I Learn

- All schools to work with topics in science/history/math by explaining things to others

- Denmark to coordinate; Deadline: LA in Italy

* A40 Would You Be My Valentine?

- Sending Valentine/Friendship cards to each other- how to do?

* A41 Invitation to LA in Italy (design a poster)

- Italy to coordinate. Deadline: beginning of March 2018

* A42 Pass It on

- Flash mobs in your local area to spread the word of Erasmus+

- Films to be shared. Deadline:

* A44 Evaluation of the project with pupils and staff

- Italy to coordinate. Deadline: beginning of May 2018

* A45 Thank You photo

- All schools; Shared in e-twinning, webpage and in print in TPM Spain May 2018

**4. LEARNING ACTIVITY IN ITALY: LANGUAGE LEARNING APRIL 15th – 19th**

***(=work days- travel days April 14th + 20th)***

- Italy to present: plans for travel, accommodation for teachers , host families for children, program

**5. TPM IN SPAIN : FINAL EVALUATION May 19th – 24th 2018**

- Spain to present: plans for travel, accommodation for teachers, ideas for the program

- We need time for evaluation!

Greetings,

Elisa