**TIMETABLE**

**Id Activity Type Starting**

**Period Description**

P1 Other Project Events 09-2019

ERASMUS+ TEAMS:

- The establishment of the ERASMUS+ project team in each kindergarten (the team is made up of: coordinator, deputy coordinator, all teachers participating in the project, parents' representatives)

- The division of roles and the establishment of persons responsible for individual activities in the project-

- The establishment of the rules of cooperation between the project partners (the Polish partner is responsible)

- The information to the teachers, students, parents, local authorities, community and media about the project goals and planned activities

- The information meeting for parents interested in participating in foreign mobilities and hosting families from partner countries

- The establishment of the rules of the families' travelling and hosting

- The creation of a detailed breakdown of the project budget, in accordance with the principles of efficiency and economy

P2 Other Project Events 09-2019

ERASMUS+ TEAMS:

- Creating a banner with the project name, participants, information on co-financing it by the EU (Erasmus+ logo) - at the entrance to the kindergarten

- The ERASMUS+ project corner creation

- The creation of the project blog (the Romanian partner is responsible)

- The first information on the eTwinning platform (the Spanish partner is responsible)

- The presentation of the project in social media and in each kindergarten website

- The calendar of meetings for the preparation of the different activities (the Polish partner is responsible)

- Preparation of a printable booklet to know the partner countries: location in Europe, flag, etc. (the Lithuanian partner is responsible)

- The establishment of the cooperation with the municipal public library and other local institutions in each partner country

- Joining in the campaign “All of Europe Reads to Kids” (the Italian partner is responsible)

- Dissemination of information on the eTwinning platform and on the project blog

P3 Other Project Events 09-2019

STUDENTS:

- The International Day of the Dot (15th September) with art activities (the Polish partner is responsible)

- The European Day of Languages celebration (26th September) with the videoconference (the Greek partner is responsible)

- Looking for and completing the information about partner countries - flags of partner countries activity (the beginning preparation of albums about partner countries)

- Mornings/afternoons with the literature for children (weekly reading activities) from the project “Golden List of Books”

P4 Other Project Events 10-2019

ERASMUS+ TEAMS:

- The project mascot creation

- The project backpacks with an official project logo will be given to all the members as a dynamic and diffusion element of our European project

- Creating a questionnaire to investigate families' reading habits and attitudes towards reading

- Dissemination of information on the eTwinning platform and on the project blog

- Portfolio for students (Polish partner is responsible)

P5 Other Project Events 10-2019

STUDENTS:

- Looking for and completing the information about partner countries - activities with the geographical atlas (continuing work with albums about partner countries)

- The project logo contest - the victorious project of logo (chosen by voting of all countries) will represent the project and will figure in the official and dissemination documents of the project

- Creating mind maps, word clouds about e.g. the benefits of reading (pupils) by using ICT tools

- Mornings/afternoons with the literature for children (weekly reading activities) from the project “Golden List of Books”

C1 Short-term exchanges of groups of pupils 11-2019 LET'S DISCOVER EACH OTHER!

P6 Other Project Events 11-2019

ERASMUS+ TEAMS:

- The substantive and cultural preparation for a visit to Italy

- Meeting with families participating in the foreign mobility

- Dissemination of information on the eTwinning platform and on the project blog

P7 Other Project Events 11-2019

STUDENTS:

- The project song creation activity

- The presentation of each country, city and kindergarten - activity held with children and for children. Results will be shown during the meeting in Italy

- Mornings/afternoons with the literature for children (weekly reading activities) from the project “Golden List of Books”

P8 Other Project Events 12-2019

ERASMUS+ TEAMS:

- After the visit to Italy: the open information session (with presence of the families participating in foreign mobility) about achieved goals and results – for students, parents, the kindergarten staff, local authorities and media

- The transnational Learning, Teaching and Training activity in Italy evaluation by its participants from partner countries (teachers, children and parents)

- Preparing materials for the newsletter (Lithuanian partner is responsible)

- Dissemination of information on the eTwinning platform and on the project blog

- Periodic monitoring of implementation of the budget and potential modifications (each partner coordinator is responsible)

P9 Other Project Events 12-2019

STUDENTS:

- Supplementing by students and parents the album about Italy with photos, souvenirs, drawings, etc.

- History of paper activities, who is attributed the invention, paper diversity

- The presentations about the history of paper and the "need for its use". How would the development of the history have been without paper, books? - brainstorming

- The first civilizations using paper and normalizing its use

- Investigation about the different types of paper and their different uses

- The visit to paper factory. The visit to a paper and cardboard factory to learn about its manufacture

- Christmas activities: preparing and sending Christmas cards; workshops about Christmas tradition; Christmas wishes and songs – the videoconference. Christmas decorations with recycled paper

- Mornings/afternoons with the literature for children (weekly reading activities - Christmas story) from the project “Golden List of Books”

P10 Other Project Events 01-2020

ERASMUS+ TEAMS:

- Dissemination of information on the eTwinning platform and on the project blog

P11 Other Project Events 01-2020

STUDENTS:

- First writing information (the first written manifestations and their different codes, symbols and spellings)

- Evolution of the history of writing

- Different types of writings

- First books, conservation and transmission. The way to preserve them in order to transmit their content

- The printing press (Johannes Gutenberg), evolution and invention of the printing press, different kinds of writing instruments. First mechanically printed books

- Mornings/afternoons with the literature for children (weekly reading activities) from the project “Golden List of Books”

P12 Other Project Events 02-2020

ERASMUS+ TEAMS:

- The substantive and cultural preparation for a visit to Spain

- Meeting with families participating in the foreign mobility

- Dissemination of information on the eTwinning platform and on the project blog

P13 Other Project Events 02-2020

STUDENTS:

- The visit to the print shop (familiarization with the profession of the printer, bookbinder). The transition from mechanics to computer science in the printing press

- The creation of the leaflets / posters promoting the STORY BOOK project, both on paper and in digital mode

- Recycling. Development a paper recycling plan and being aware of the optimization of its use

- Mornings/afternoons with the literature for children (weekly reading activities) from the project “Golden

List of Books”

C2 Short-term exchanges of groups of pupils 03-2020 WHAT A BOOK IS MADE FROM?

P14 Other Project Events 03-2020

ERASMUS+ TEAMS:

- After the visit to Spain: the open information session (with presence of the families participating in foreign mobility) about achieved goals and results

- for students, parents, the kindergarten staff, local authorities and media

- The transnational Learning, Teaching and Training activity in Spain evaluation by its participants from partner countries (teachers, children and parents)

- Preparing materials for the newsletter (Lithuanian partner is responsible)

- Dissemination of information on the eTwinning platform and on the project blog

P15 Other Project Events 03-2020

STUDENTS:

- Supplementing by students and parents the album about Spain with photos, souvenirs, drawings, etc.

- The creation a reading corner in kindergarten

- Where can we find books? - activities

- The visit to the bookstore (a child books presentation, workshops)

- The afternoon / evening with a famous writer for students and parents

- Mornings/afternoons with the literature for children (weekly reading activities) from the project “Golden List of Books”

P16 Other Project Events 04-2020

ERASMUS+ TEAMS:

- Dissemination of information on the eTwinning platform and on the project blog

P17 Other Project Events 04-2020

STUDENTS:

- The creation a small library in the kindergarten

- The visit to the local library (familiarizing with the profession of the librarian, rules of behaviour)

- The International Day of the Book for Children (2nd April) activities

- The reading promotion campaign

- Easter tradition activities (workshops with parents, the videoconference between partners)

- Mornings/afternoons with the literature for children (weekly reading activities) from the project “Golden List of Books”

C3 Short-term exchanges of groups of pupils 05-2020 LOOKING FOR A BOOK

P18 Other Project Events 05-2020

ERASMUS+ TEAMS:

- The substantive and cultural preparation for a visit to Lithuania

- Meeting with families participating in the foreign mobility

- Dissemination of information on the eTwinning platform and on the project blog

P19 Other Project Events 05-2020 STUDENTS:

- The Europe Day (9th May) happening

- A visit to the reading room

- Becoming the reader - the celebration and activities held in the cooperation with the local library

- Mornings/afternoons with the literature for children (weekly reading activities) from the project “Golden List of Books”

P20 Other Project Events 06-2020

ERASMUS+ TEAMS:

- After the visit to Lithuania: the open information session (with presence of the families participating in foreign mobility) about achieved goals and results

- for students, parents, the kindergarten staff, local authorities and media

- The transnational Learning, Teaching and Training activity in Lithuania evaluation by its participants from partner countries (teachers, children and parents)

- Preparing materials for the newsletter (Lithuanian partner is responsible)

- Periodic monitoring of implementation of the budget and potential modifications (each partner coordinator is responsible)

- The summary of the first year work in the project (the intermediate report)

P21 Other Project Events 06-2020

STUDENTS:

- BOOK STORY summarizing activities (exhibition, performance, etc.) - for students, parents, the kindergarten staff, local authorities and media

- Supplementing by students and parents the album about Lithuania with photos, souvenirs, drawings, etc.

- Mornings/afternoons with the literature for children (weekly reading activities) from the project “Golden List of Books”

P22 Other Project Events 09-2020

ERASMUS+ TEAMS:

- The information to the teachers, students, parents, local authorities, community and media about the project goals and planned activities

- The information meeting for parents interested in participating in foreign mobilities and hosting families from partner countries

- The establishment of the rules of the families' travelling and hosting

- Dissemination of information on the eTwinning platform and on the project blog

P23 Other Project Events 09-2020 STUDENTS:

- The International Day of the Dot (15th September) with art activities (the Polish partner is responsible)

- The European Day of Languages celebration (26th September) with the videoconference (the Greek partner is responsible)

- Establishing the list of readings to be addressed: stories and fables from national and universal children’s literature

- The meeting with the writer (workshops including brainstorming, inspiration, feelings, emotions)

- The diary “Ideas from the little writers” – the creation by children their own story and their own book

- The afternoon / evening reading for students and parents

- Mornings/afternoons with the literature for children (weekly reading activities) from the project “Golden List of Books”

P24 Other Project Events 10-2020

ERASMUS+ TEAMS:

- Dissemination of information on the eTwinning platform and on the project blog

P25 Other Project Events 10-2020

STUDENTS:

- Happening “Grandparents in kindergarten”

- The meeting with the illustrator - practices on small illustrations

- Children will continue the story started before, by drawing

- Mornings/afternoons with the literature for children (weekly reading activities) from the project “Golden List of Books”

C4 Short-term exchanges of groups of pupils 11-2020 WHAT BOOK AM I? READ ME!

P26 Other Project Events 11-2020

ERASMUS+ TEAMS:

- The substantive and cultural preparation for a visit to Romania

- Meeting with families participating in the foreign mobility

- Dissemination of information on the eTwinning platform and on the project blog

P27 Other Project Events 11-2020 STUDENTS:

- The meeting with the proofreader, the publisher (familiarization with the professions)

- The children complete their story and book and present it to the group

- Mornings/afternoons with the literature for children (weekly reading activities) from the project “Golden List of Books”

P28 Other Project Events 12-2020

ERASMUS+ TEAMS:

- After the visit to Romania: the open information session (with presence of the families participating in foreign mobility) about achieved goals and results

- for students, parents, the kindergarten staff, local authorities and media

- The transnational Learning, Teaching and Training activity in Romania evaluation by its participants from partner countries (teachers, children and parents)

- Preparing materials for the newsletter (Lithuanian partner is responsible)

- Dissemination of information on the eTwinning platform and on the project blog

- Periodic monitoring of implementation of the budget and potential modifications (each partner coordinator is responsible)

P29 Other Project Events 12-2020

STUDENTS:

- Supplementing by students and parents the album about Romania with photos, souvenirs, drawings, etc.

- The history of writing in caves (pictures)

- The rebus contest activity

- Christmas activities: preparing and sending Christmas cards; workshops about Christmas tradition; Christmas wishes and songs – the videoconference

- Mornings/afternoons with the literature for children (weekly reading activities - Christmas story) from the project “Golden List of Books”

P30 Other Project Events 01-2021

ERASMUS+ TEAMS:

- Dissemination of information on the eTwinning platform and on the project blog

P31 Other Project Events 01-2021

STUDENTS:

- Various kinds of letters (Latin, Hebrew, Arabic, Greek, Cyrillic, Chinese alphabets) - art workshops

- Different kinds of communication (Braille alphabet, Morse code, signals with flags, etc.)

- The coding activities

- Mornings/afternoons with the literature for children (weekly reading activities) from the project “Golden List of Books”

P32 Other Project Events 02-2021

ERASMUS+ TEAMS:

- The substantive and cultural preparation for a visit to Poland

- Meeting with families participating in the foreign mobility

- Dissemination of information on the eTwinning platform and on the project blog

P33 Other Project Events 02-2021

STUDENTS:

- Pictograms (children create their own ones)

- Traffic signs and road safety activities

- Mornings/afternoons with the literature for children (weekly reading activities) from the project “Golden List of Books"

C5 Short-term exchanges of groups of pupils 03-2021 “READING” AND “WRITING”

P34 Other Project Events 03-2021

ERASMUS+ TEAMS:

- After the visit to Poland: the open information session (with presence of the families participating in foreign mobility) about achieved goals and results

- for students, parents, the kindergarten staff, local authorities and media

- The transnational Learning, Teaching and Training activity in Poland evaluation by its participants from partner countries (teachers, children and parents)

- Preparing materials for the newsletter (Lithuanian partner is responsible)

- Dissemination of information on the eTwinning platform and on the project blog

P35 Other Project Events 03-2021

STUDENTS:

- Supplementing by students and parents the album about Poland with photos, souvenirs, drawings, etc.

- The visit to a photo shop (workshops about how to take a good photo)

- The reading promotion campaign

- Pupils as the reporters (interviews, photo-reports, videos about the reading promotion campaign to the local media)

- Easter tradition activities with students and parents

- Mornings/afternoons with the literature for children (weekly reading activities) from the project “Golden List of Books”

P36 Other Project Events 04-2021

ERASMUS+ TEAMS:

- Dissemination of information on the eTwinning platform and on the project blog

P37 Other Project Events 04-2021

STUDENTS:

- The International Day of the Book for Children (2nd April) activities

- The afternoon / evening with a writer for students and parents

- Listening to the audiobooks for children

- Powerpoint presentation or video about various project events

- Mornings/afternoons with the literature for children (weekly reading activities) from the project “Golden List of Books”

C6 Short-term exchanges of groups of pupils 05-2021 BOOKS AND NEW TECHNOLOGIES

P38 Other Project Events 05-2021

ERASMUS+ TEAMS:

- The substantive and cultural preparation for a visit to Greece

- Meeting with families participating in the foreign mobility

- Dissemination of information on the eTwinning platform and on the project blog

P39 Other Project Events 05-2021

STUDENTS:

- The Europe Day (9th May) happening

- Becoming the reader - the celebration and activities held in the cooperation with the local library

- Activities on tablets or digital boards (web tools for students workshops)

- Mornings/afternoons with the literature for children (weekly reading activities) from the project “Golden List of Books”

P40 Other Project Events 06-2021

ERASMUS+ TEAMS:

- After the visit to Greece: the open information session (with presence of the families participating in foreign mobility) about achieved goals and results

- for students, parents, the kindergarten staff, local authorities and media

- The transnational Learning, Teaching and Training activity in Greece evaluation by its participants from partner countries (teachers, children and parents)

- Preparing materials for the newsletter (Lithuanian partner is responsible)

- Dissemination of information on the eTwinning platform and on the project blog

- Periodic monitoring of implementation of the budget and potential modifications (each partner coordinator is responsible)

- The summary of the second year work in the project (the final report)

P41 Other Project Events 06-2021 STUDENTS:

- BOOK STORY summarizing activities (exhibition, performance, etc.) - for students, parents, the kindergarten staff, local authorities and media

- Supplementing by students and parents the album about Greece with photos, souvenirs, drawings, etc.

- Mornings/afternoons with the literature for children (weekly reading activities) from the project “Golden List of Books”