**Erasmus+ Programme Call 2019 - KA2 Strategic Partnership for Cooperation for Innovation and Good Practices**

**This meeting: Thursday 3rd February 2022 on web**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Institution** | **Country** | **Contact person** | **Email** | **Participated** |
| AE S. João da Talha | Portugal | Cristina Maia | cmaia@aesjt.pt | X |
| AE S. João da Talha | Portugal | Cristina Fonseca Santos | cfsantos@aesjt.pt |  |
| AE S. João da Talha | Portugal | Carla Almeida | calmeida@aesjt.pt | X |
| AE S. João da Talha | Portugal | David Santos | dsantos@aesjt.pt |  |
| Publiczna Szkola Podstawowa nr 17 im.Przyjaciol Dzieci w Radomiu | Poland | Monika Gorecka | monikagorecka@o2.pl | x |
| 10O Gymnasio Hrakleioy | Greece | Alexis Tzormpatzakis | alexistzormpatzakis@gmail.com | x |
| Saint Paul’s Missionary College | Malta | Alexia Micallef Gatt | alexia.micallefgatt@spmc.edu.mt | x |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

**Work in progress for CLearn project**

|  |  |  |  |
| --- | --- | --- | --- |
| **Topic** | **Issue** | **Deadline** | **Responsibility** |
| Third LTTA  | Transnational project meeting in Poland4th – 8th April |  | All |
| eTwining | Collection of all the workprocess |  | Malta |
| Website(in the making) | Videos – eBook – online exhibition (in the making) |  | Greece |
| eBook(in the making) | Pictures from each country – transnational meetings 20Preparing the activities 20 | Greece sends pictures from 1st transnational meeting – 30th October | Portugal |
| Evaluation of the activities(from Portugal -already in the classroom) | RubricsOnline survey in the classroom | 30th October | PortugalPoland |
| Online Exhibition(not started yet)  | Pictures from each country  | Same pictures | Portugal |
| Videos(some already sent) | Each country sends to AlexisVideos from each country: preparing the activities | 30th October  | All |
|  |  |  |  |
|  |  |  |  |

Next meeting is: Before LTTA in Poland. Date to be set.