Main milestones

- Scheduling of activities
- Preparing evaluation forms which should be filled-in by all partners to give feedback about evaluation of activities and evaluation of the meetings

Task list for the next steps and deadlines
W	Task	Who?	When?	Deadline
W1 / management	create a lesson plan for peers and younger students	all	From december 2016	March 2018
W2 / management	Set up and management of google drive, Twinspace, Moodle platform	Italian ambassadors / and all teachers	From september 2016	Septtember 2019
W3 / planning	General researches on natural hazards and on geology, risk of 'natural ' disaster or disaster due to human activities in each country ( Focus on earthquakes and eruptions; water scarcity., increase of invasive alien species and biodiversity,events related to climate change, floods, landslides, melting glaciers, hott summers..)	all	From december 2016	March 2018
W4 / implementation	Monitor the calamitous events in region and every six months a google fusion map and a mathematical comparison of the events between each region will be published / Students will study and examine in depth the cutting edge technologies for the monitoring of geophysical phenomena on a large scale and for risk reduction ( satellites, GPS...)	all	From september 2016	Septtember 2019
W5 / implementation	Evaluation, monitoring of the project activities.	all	From september 2016	Septtember 2019
W6 / Dissemination	Elaboration of a dissemination and exploitation strategy for each partner country	All student ambassadors	From december 2016	Septtember 2019
W7 / Dissemination	A project leaflet and a project poster should be developed	All	From december 2016	April 2018

We prepaared the evaluation form template