Online meeting Erasmus + project « Empower students’well-being »
04/10/2020

Hatice Keskin, Turkish coordinator
Claudia Oprise, Romanian coordinator
Malgorzata Sokolowska, Polish coordinator
Jerome Vallot, French coordinator and coordinator of the project

1/ ErasmusDays 15-17/10/2020

a/ Video celebrating the event

Poland is responsable for the creation of the video with the rushes sent by the other 3 countries. This video will be uploaded in the Twinspace.

b/ Padlet « moving without planes »

Poland will create 1 common Padlet with some records from the 4 countries. The Padlet will be uploaded in the Twinspace.

c/ Local events

France : The lycee will take part in an event organised by the DAREIC (see the Twinspace «Le Greenspace : l'Europe en vert et pour tous ! Les ErasmusDays 2020 de l'Académie d'Aix-Marseille »).

Poland : Participation in a running race. 4 students will run for 1 hour in the parc of Raciborz castle. The goal is to run a distance as long as possible. The other students will come to support the athletes. A video of the event will be taken.

Romania : The students will create some posters representing their personal image of the city of Marseille.

Turkey : A puzzle game with pictures taken in Düzce will be organised. An online conference about the didactic of distance learning was organised for the teachers of the school. A video of the Erasmus Days will be created.

2/ Videos Matilda

Turkey and Poland will upload their videos by the 15th of December 2020.

A script from the Romanian video will be sent to the coordinator by the 15th of December 2020.

3/ The Erasmus + Project Results platform (E+PR) :

Differents products will be sent to the coordinator :
- script of the Romanian drama play
- description of the Turkish games done in Düzce
- instructions for the Polish dance
4/ Contract extension

The contract is definitely extended to the end of February 2022.

5/ Other questions

The next online meeting will be organised with the chatroom of the Twinspace, Sunday, 08/11/2020, at 8 p.m. French time.