| M1 Sep | M2 (Oct) | M3 (Nov) | M4 ( Dec) | M5 (Jan) | M6 (Feb) | M7 (Mar) | M8 (Apr) | M9 (May) | M10 (June) | M11 (July) | M12 (Aug) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A1 Designing Logo/ badge |  | A2 news on project | M1 ( 1st TPM)Rybnik A5 (dropout rates, Hattie’s checklist) | A2 Reporting/releasing press articles/ interviews/ news on project progress informing the target audience about project progress and project outputs using the following channels ( press release/ flyers/ school websites/teacher meetings/school magazines/ school radio) | Implementing conclusions from 1st TPM |  | A3 Designing methods and educational materials, questionnaires, TEPs, Individual School Development Plans C1 ( STTTE) Germany | A2 Reporting/releasing press articles/ interviews/ news on project progress informing the target audience about project progress and project outputs using the following channels ( press release/ flyers/ school websites/teacher meetings/school magazines/ school radio) | E1 Organizing workshops at local schools based on results /outputs worked out during TPMs and training events - Organizing local school events for students to implement project results ( creative ideas after TPMs and training/learning events) - Cooperating with local/ regional schools ( organizing events/ conferences) with certification - Involving experts in workshops/events/interviews to disseminate/ promote project results | A2 Reporting .. |  |
| M13 (Sep) | M14 (Oct) | M15 (Nov) | M16 (Dec) | M17 (Jan) | M18 (Feb) | M19 (Mar) | M20 (Apr) | M21 (May) | M22 (June) | M23 (July) | M24 (Aug) |
| A5 Measuring change |  | A3 Designing tools / implementation methods/ ater experts’ comments M2 (2nd TPM) Italy | A2 reporting on project progress… | A4 Supervising students' online work ( blended mobility) and providing them with professional support | A3 Designing methods and educational materials, questionnaires, TEPs, Individual School Development Plans C3 additional ( STSTE, additional blended mobility for BG students and other partners depending on available budget) PT | A2 reporting on project progress… | A4 Supervising students' online work ( blended mobility) and providing them with professional support | A3 Designing methods and educational materials, questionnaires, TEPs, Individual SchoolDevelopment Plans C3 (STSTE – blended mobility for students) BG | A2 Reporting/releasing press articles/ interviews/ news on project progress informing the target audience about project progress and project outputs using the following channels ( press release/ flyers/ school websites/teacher meetings/school magazines/ school radio) E2 Organizing workshops at local schools based on results /outputs worked out during TPMs and training events - Organizing local school events for students to implement project results ( creative ideas after TPMs and training/learning events) - Cooperating with local/ regional schools ( organizing events/ conferences) with certification - Involving experts in workshops/events/interviews to disseminate/ promote project results |  | A4 Supervising students' online work ( blended mobility) and providing them with professional support |
| M25 (Sep) | M26 (Oct) | M27 (Nov) | M28 (Dec) | M29 (Jan) | M30 (Feb) | M31 (Mar) | M32 (Apr) | M33 (May) | M34 (June) | M35 (July) | M36 (Aug) |
| A5 Measuring change | A3 Designing methods and educational materials, questionnaires, TEPs, Individual School Development Plans C2 (STTTE) (Fi) | A2 Reporting | E3 Organizing workshops at local schools based on results /outputs worked out during TPMs and training events - Organizing local school events for students to implement project results ( creative ideas after TPMs and training/learning events) - Cooperating with local/ regional schools ( organizing events/ conferences) with certification - Involving experts in workshops/events/interviews to disseminate/ promote project results |  | A3 Designing methods and educational materials, questionnaires, TEPs, Individual SchoolDevelopment Plans | A2 Reporting on project progress | A5 Measuring change Assessment based on 2 aspects: 1.Quantitative e.g. the number of diplomas, average grades in final exams, number of students who leave school with specific perspective (university, internship, training). 2. Qualitative aspects gained through students/teachers questionnaire about learning habits, changes and the outcomes | A3 Designing methods and educational materials, questionnaires, TEPs, Individual School Development Plans M3 (3rd TPM) Poland | A2 Reporting/releasing press articles/ interviews/ news on project progress informing the target audience about project progress and project outputs using the following channels ( press release/ flyers/ school websites/teacher meetings/school magazines/ school radio) E4 Organizing workshops at local schools based on results /outputs worked out during TPMs and training events - Organizing local school events for students to implement project results ( creative ideas after TPMs and training/learning events) - Cooperating with local/ regional schools ( organizing events/ conferences) with certification - Involving experts in workshops/events/interviews to disseminate/ promote project results |  | A2 additional after experts’ evaluation |

| *Project activity types: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | An | - PROJECT MANAGEMENT AND IMPLEMENTATION ACTIVITIES |
|  | On/An | - INTELLECTUAL OUTPUTS/ACTIVITIES |  |  |  |  |
|  | Mn | - TRANSNATIONAL PROJECT MEETINGS |  |  |  |  |
|  | En | - MULTIPLIER EVENTS |  |  |  |  |  |  |  |  |
|  | Cn | - LEARNING/TEACHING/TRAINING ACTIVITIES |  |  |
|  | n | - number of the activity |  |  |  |  |  |  |  |

AF     p.42

- ( reduced) 3  TPMs  ( Transnational Project meetings)   Poland, Italy. Poland     M1, M2, M3

- 2 STTEs  ( Short Term Teacher Training Events) ( detailed description in the AF  section G1 )  C 1 , C2

-1 SSTE    ( Short Term Student Training/Learning  Event - blended mobility)  (C3 May 2019) additional C3  ( Feb 2019)

- Involving local experts  in training events, (C1-C3)

- Involving local teachers, principals, students in STST/STT events  (C1-C3)

- Designing a project logo and a badge for schools who will apply project results/ methods/ approaches  (A1)

- Reporting/releasing press articles/ interviews/ news on project progress:

( regularly  after each TPM and training/learning events); informing  the target audience  about  project progress and

project outputs using  the following channels ( press release/ flyers/ school websites/teacher meetings/school magazines/ school

radio) (A 2)

- Organizing workshops at local schools based on results /outputs worked  out during TPMs and training events (E 1-4)

- Organizing  local school events for students to implement project results ( creative ideas after TPMs and training/learning events)

(E1-4)

- Cooperating with local/ regional schools ( organizing events/ conferences) with certification (E1-4)

- Involving experts  in workshops/ events/interviews to disseminate/ promote project results (E1-4)

- Designing methods and educational materials, questionnaires, TEPs, Individual School Development Plans  (A3)

- Organizing Erasmus plus  information corners in every partner school  (throughout the whole project life)

- Organizing support for disabled/SEN students while involving them in project activities (during the whole project life)

- Supervising students' online work ( blended mobility) and providing them with professional support (A 4)

- Measuring change (A5)

Assessment will be based on two kinds of aspects:

1. Quantitative aspects like the number of diplomas, average grades in final exams, number of students who leave school with

a specific perspective (university, internship, training).

2. Qualitative aspects gained through  students/teachers questionnaire about learning habits, changes and the outcomes.

- Providing linguistic support for students/ teachers involved in mobilities ( if relevant)

- Equipping schools with professional educational materials by Prof. John Hattie ( books, articles, subscriptions)

- Designing project promotional materials/ invitations/ folders/a variety of materials for dissemination

- Cooperating with local/regional  agents/stakeholders / policy makers ( communication)

- Presenting  the outcome on posters to be hung out at schools

- Distributing  materials from workshops amongst staff members

- Meeting in Project groups to prepare for TPMs and Training/ Learning Events ( using specially designed materials/ presentations)

(before TPMS and Training /Learning events)

- Meeting during Coordinator meetings ( using specially prepared materials) (TPMs)

- Applying relevant  information storage devices ( digital devices / pendrives/ CDs/ written sets of materials)

- Using specially designed materials/innovative equipment  for implementing feedback/ strategies/ evaluation/ other relevant

educational interventions chosen on the basis of research into  Prof. Hattie's approach;  also resulting from inspiration

after exchanging good  practices

- Creating materials to promote positive mindset towards inclusion

- Promoting the project and its results during school open days ( according to school  itineraries)

- Making interviews/questionnaires/Performance pool with OERs

- Applying collaboration work tool ( Azendoo) for complex  planning, task distribution, monitoring, SWOT analysis, storing data and

for complex project management and implementation  (regularly)

- Handling organizational work/budgeting/contracting/cooperating with the accounts department /NAs/relevant local institutions

- Attending meetings for project coordinators organized by NAs

- Regular reporting with the use of MT(Mobility tool) ( after each mobility)

symbols used A, C, E  ( refer to activities described in the Gantt-chart-template )