EU-ROBOTIK STEM PROJECT SCHEDULE

| Months | Subject | Tools / Methods | Notes |
| --- | --- | --- | --- |
| JANUARY | Creation of Project’s virtual class | Edmodo.com | A virtual class will be created to Edmodo for students and teachers to join. This will help excanging ideas, material, setting tasks and assignments and the communication of the project. |
|  | Logo and Poster design for the project. STEM poster design | Free to Use Web2 Tools | Partner teams will design the project’s logo and posters about the project. Special STEM posters for each STEM element (Science, Technology, Engineering, Math) will be created by students. |
| FEBRUARY | Research on nuclear waste. | Research Web. Posting of materials to Padlet | Learners will learn about nuclear waste. There will be posters, wordclouds, slayt sor videos about nuclear waste. |
|  | Common assignment of tasks to be done by the robot who handles and transfers radioactive waste. | Discussion on Edmodo and articles on Padlet | There will be brainstorming on padlet to decide on tasks to be performed by robot. At the end of month there will be one list about the tasks of robots |
| MARCH | Design and construction of Robots. Coding activities for learners. Study and use of STEM elements for the above processes. | Lego EV3-G S4A(Scratch for Arduino) Lego Digital Designer Free to Use Web2 Tools | Each partner can have different way to collect nuclear waste, each partner will create own design of Robot and coding. (take photo and video, use web2 tools to combine them) |
| APRIL | Design of testing mats for the robots to be tested. Testing programms and robot models. | Lego EV3-G S4A(Scratch for Arduino) Free to Use Web2 Tools | Each partner will create a testing mat that will simulate a nuclear waste environment like a waste storage, a spill etc. Each partner will start testing activities. (take photo and video, use web2 tools to combine them) |
| MAY | Exhibition of all the pictures and videos taken during the preparatory period | Free to Use Web2 Tools | Each partner will organise own exhibition |
|  | (Optional) Programming a visit with the aggreement of all partners and exhibition in one hosting partner. Preparation of produced material (posters, brochures etc), about the project for robotics where will be hold | Free to Use Web2 Tools | Each partner will have it will be a display area at host instution for exhibition of robots. |
| JUNE | Fair of the Project at ……. (place will be decide together) E-Book of the Project Evaluation of the Project | Free to Use Web2 Tools | The fair will be organized at one of partner school, partners will be free to participate for the fair. There will be a e-book of the project, which will include all the process. |

A.Anıl TOROS

Project Coordinator