## KA2_SP_TIMELINE_TEMPLATE
Name of the project: | [please complete the name of the project as in the application form]
PROJECT TIMETABLE
| MONTHS | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M34 | M35 | M36
Project activity*
A1 |  | M3: Project BLOG
A2 |  | M1: E-TWINNING
A3 |  | M1: Logo and K2 corner-NOTICE BOARD
A4 |  | M1: Pre-Scheduling between coordinators
A5 |  | M2: INTERNAL MEETINGS (each school); M14: INTERNAL MEETINGS (each school)
A6 |  | M2: SKYPE VIDEOCONFERENCES Calendar; M13: SKYPE VIDEOCONFERENCES Calendar
A7 |  | M2: SCHOOL SYSTEMS PRESENTATIONS during Mobilities
A8 |  | M2: 1st European topic/theme; M7: 2nd European topic/theme; M14: 3d European topic/theme; M19: 4th European topic/theme
A9 |  | M4: Teaching Units; M7: Teaching Units; M14: Teaching Units
A10 |  | M2: EVALUATION-SAT; M9: EVALUATION-SAT; M21: EVALUATION-SAT
A11 |  | M2: Planning activities; M14: Planning activities
A12 |  | M2: Questionn. 1-2-3; M6: Quest. 4; M8: Questionn. 5-6; M14: Questionn. 1-2-3; M18: Quest. 4; M20: Quest. 6; M22: Questionn. 3-5
A13 |  | M2: Plan to discuss and adjust the SAT: SCHOOL ASSESSMENT TOOL
A14 |  | M20: Collecting analysis for the final SAT: SCHOOL ASSESSMENT TOOL
A15 |  | M21: Spreading the IOs
A16 |  | M4: TT Topics: How to read a painting; Geometry using CLIL
A17 |  | M7: TT Topics: Environment; Rubbish? Re-duce, Re-use, Re-cycle
A18 |  | M14: TT Topics: Holocaust; Traditional Folktales /Fairy-Tales and Propp’s narrative functions
A19 |  | M19: TT Topics: Traditional sport games and plays; the Finnish School System
A20 |  | M24: ERASMUS+ PROJECT RESULTS
A21 |  | M21: SAT dissemination
C1 |  | M4: Romania: Short-Term Staff Training
C2 |  | M7: Lithuania: Short-Term Staff Training
C3 |  | M14: Spain: Short-Term Staff Training
C4 |  | M19: Finland: Short-Term Staff Training
E1 |  | M22: Italy: Multiplier Event
E2 |  | M22: Finland: Multiplyer event
E3 |  | M22: Lithuania: Multiplier Event
E4 |  | M22: Poland: Multiplier Event
E5 |  | M22: Romania: Multiplier Event
E6 |  | M22: Spain: Multiplier Event
E7 |  | M22: Greece: Multiplier Event
M1 |  | M2: Italy: TM
M2 |  | M9: Poland
M3 |  | M21: Greece: TM
Please insert rows as needed
*Project activity types:
| An | M1: - PROJECT MANAGEMENT AND IMPLEMENTATION ACTIVITIES
| On/An | M1: - INTELLECTUAL OUTPUTS/ACTIVITIES
| Mn | M1: - TRANSNATIONAL PROJECT MEETINGS
| En | M1: - MULTIPLIER EVENTS
| Cn | M1: - LEARNING/TEACHING/TRAINING ACTIVITIES
| n | M1: - number of the activity
Please enter all main project activities and meetings, intellectual outputs and related activities, multiplier events and training/teaching/learning activities. Use the reference numbers as they appear in the application form. Where no numbers exist in the application form (i.e. for activities included in project management and implementation), use reference numbers A1, A2 etc. For each activity, meeting or event, indicate the month(s) in which they will be produced/take place by colouring the corresponding cells.