**Transnational Project Meeting and Multiplier Event**

Place: Brekkuskóli in Akureyri, Iceland

Dates: March 26th-30th 2017

**AGENDA**

**1. Welcome to all!**

Wales: Paul, Catrin, Carwen

Italy: Luca, Alessandra, Maria Elena

Denmark: Elisa, Mie, Søren

Germany: Wiete, Christine, Jan

Iceland: Helga & co

Spain: Carolina, Maria José, David

**We go through the programme for the TPM and Multiplier Event.**

**2. REVIEWING THE CURRENT PROJECT ACTIVITIES**

* **The Culture Quilt A4**

Iceland to present and hand out pieces for all partner schools.

* **Design a T-shirt for your school A20**

We exchange experiences with this activity.

* **Guest Teachers A21 (All)**

Exchange of experiences/ideas. Deadline : end of May 2017.

Denmark would like to prolong this activity.

* **Visit at the local museums/cultural visits A8**

Exchange experiences. Deadline: end of 2017.

* **Investigating local creative companies A22**

Denmark would like to prolong this activity until Christmas 2017.

* **Famous artist of your town/country/region A28 (Spain)**

Pupils work learning, imitating and interpretating an artist and his/her style of art. There will be produced material for the partner countries to use (worksheets, power points).

Spain has added a format in the wikispaces. .All countries produce a Teaching Package for one of the artists in their country/region. This work will be shared in LA in Germany in the ***end of April 2017***

* **LCC Birthday Calendar A25**

1. ***A combination of photos/drawings;***

- 8/country about the sights/locations that children like in their community

- 1 in the back cover about “Learn Create Communicate”

=> in all 9 photos/ drawings about what you see/like in your local area

MONTHS: Jan+April- Spain; Feb+Sept – Italy; March+ June – Iceland; May+Oct – Germany; July+ Nov – Wales; Aug+Dec- Denmark

REMEMBER: Behind each photo: the name of the school + pupil´s name + month

=> take along to LA in Germany to hand in to Kamilla/Mette

2**. Suggestions to front cover**

5/country about Internationality & birthdays

=> take along to LA in Germany

=> a vote for the cover between all pupils

Deadline for the calendar: TPM in Denmark in October 2017(Denmark to collate).

* **Sixty Inspiring Ideas to Teach Skills A15 (Iceland)**

Iceland will present the book and OER (Open Educational Resource)

* **Design the Poster for the 2nd LA in Germany A26 (Germany)**

Send the invitation poster to partner school and share via e-twinning. ***Deadline: End of March 2017***.

**2. PLANNING AHEAD**

* **LEARNING ACTIVITY IN GERMANY (Germany presents)**
* Dates: April 23rd-27th 2017 – Friday half day? (we need 5 whole working days)
* Students profiles, parental consents
* Each groups makes a film to present themselves/country in Germany
* Guest families and programme
* **From My Window**

**Goal: The pupils learn how different our “cultural windows” can be.**

Exchanging postcards of what you can see from your cultural window (a landscape/view in the back yard/famous place in your town/a view from your school window). **Deadline: October 2017**

* **The interim report of the second year of the project A31**

***Goal: We evaluate the effect of the project and reflect on the steps taken so far to reach our goals.***

All schools make an evaluation of the progress of the project in their school and feedback to the coordinator as well as to IC Toscanini.

Suggestion: Should we drop this as all schools have made interim reports for their agencies. Perhaps we could use them?

* **A booklet of the LA in Blücherschule (Germany) A32**

***Goal: To disseminate the activities done and things that the pupils learnt in LA in Blücherschule.***

The booklet will be collated by Blücherschule and ***shared in the TPM in Denmark***.

* **A fifty –word play (Wales) A33**

***Goal: To learn basics of the languages in our partner countries and use the words learnt.***

We learn 50 words of a language of one of our partner schools (or less if we work with younger pupils). We will make a puppet theater/animation film, using the words that we have learnt. We will share the films in e-twinning. **Deadline:**

* **Exciting Early English (Denmark) A34**

***Goal: To share best practice in teaching English for Beginners.***

We collect and share ideas for teaching English for young pupils. Each country will contribute with at least **five ideas (photos and description) to a joint Exciting Early English-** booklet that will be shared through e-twinning. A tangible booklet will also be shared in the TPM in Denmark.

**Deadline:**

* **TPM in Nordre Skole October 4th-7th 2017 (Denmark) M5**

***Goal: To review the project activities and plan forward. Evaluate and review the dissemination work. To share best practice in early language learning.***

We share project work : Culture Quilt (Denmark), the booklet of the LA in Blücherschule (Germany).

We evaluate the Multiplier Event in Iceland as well as the LA in Germany. We plan forward.

This meeting also includes a one-day Learning Activity for teachers of English for your learners. A guest teacher will give a course in Early English and provide all participants with tangible ready-to-use materials as well as “Exciting Early English”- booklet of the shared ideas.

**3. MULTIPLIER EVENT**

Programme and planning of the event.

**4. ANY OTHER ISSUES**

**Greetings,  
Elisa Haaparanta (coordinator)**

**Nordre Skole, Denmark**