## List1
Schedule
| Month | Activity | Activities - description
M1 | September 2015 | A1 | Beginnning of the project, creating ppts or videos about our schools, towns/cities and countries to introduce ourselves
M2 | October 2015 | M1 | Teachers's meeting in Italy (Salerno)
|  | A2 | Cultural/historical workshops 1 - Historical places of our regions (visiting museums, historical places)
M3 | November 2015 | A3 | Cultural/historical workshops 2 (prehistorical and ancient times; chorus of languages)
M4 | December 2015 | C1 | Meeting with pupils in Italy (Salerno)
|  | A4 | Cultural/historical workshops 3 (Christmas traditions, traditional cuisine)
M5 | January 2016 | A5 | Survey 1: experiences in Italy (e-mails, Skype meeting)
|  | A6 | Cultural/historical workshops 4 (learning dances, chorus of languages, project dictionary - daily phrases)
M6 | February 2016 | A7 | Cultural/historical workshops 5 (Folklore traditions - Shrovetide, national cuisine, folk songs and dances, legends, chorus of languages)
M7 | March 2016 | C2 | Meeting with pupils in Slovakia (Zubrohlava)
|  | A8 | Survey 2: experiences in Slovakia (e-mails, Skype meeting)
|  | A9 | Cultural/historical workshops 6 (Easter traditions, Concert of civilisation, project dictionary - daily phrases)
M8 | April 2016 | A10 | Cultural/historical workshops 7 (Early Middle Ages, legends, folk songs, project dictionary - daily phrases, dialects)
M9 | May 2016 | A11 | Cultural/historical workshops 8 (Middle Ages, legends, Walpurgis night, Youth festival in Turkey)
M10 | June 2016 | C3 | Meeting with pupils in Poland (Mielżin)
|  | A12 | Survey 3: experiences in Poland (e-mails, Skype meeting)
|  | A13 | Cultural/historical workshops 9 (Visiting some historical places in our region)
M11 | July 2016 | A14 | Evaluation of the activities and project outputs in the first year of the project, starting creating the project chronicle
M12 | August 2016 | A15 | Preparing and planning the activities in the second year of the project
M13 | September 2016 | A16 | Cultural/historical workshops 10 (Visiting some historical places in our region)
M14 | October 2016 | M2 | Teachers's meeting in Slovakia (Zubrohlava)
M15 | November 2016 | A17 | Cultural/historical workshops 11 (the Celts in Slovakia, Early Middle Ages, poetry)
M16 | December 2016 | A18 | Cultural/historical workshop 12 (Christmas traditions, traditional cuisine)
M17 | January 2017 | A19 | Cultural/historical workshops 13 (Arrival of Slaves to Slovakia, High Middle Ages, making mosaics)
M18 | February 2017 | A20 | Cultural/historical workshops 14 (Great Moravia, Late Middle Ages, cathedrals, Shrovetide, making mosaics)
M19 | March 2017 | C4 | Meeting with pupils in Turkey (Antakya)
|  | A21 | Survey 4: experiences in Turkey (e-mails, Skype meeting)
|  | A22 | Cultural/historical workshops 15 (visiting some archeological places, modern times in our region, traditional cuisine)
M20 | April 2017 | A23 | Cultural/historical workshops 16 (Easter traditions, visiting some historical places, traditional cuisine, civilizations' chorus)
M21 | May 2017 | C5 | Meeting with pupils in the Czech Republic (Přimda)
|  | A24 | Survey 5: experiences in the Czech Republic (e-mails, Skype meeting)
|  | A25 | Creating school museums
M22 | June 2017 | A26 | Creating the project chronicle
|  | A27 | Survey 6: Evaluation of the project by pupils (questionnaire)
M23 | July 2017 | A28 | Creating the project chronicle
M24 | August 2017 | A29 | Evaluation of the activities and project outputs in the second year of the project
M25 | September 2017 | M3 | Teachers's meeting in the Czech Republic (Přimda)
M26 | October 2017 | A30 | Finishing the project chronicle, evaluation and closing the project