Suggestions for splitting the workload

On Thursday, June 6th, we had a teachers meeting about how to proceed with building the robots. We came up with the following ideas:

since the cardboard models from all teams look pretty similar, let us use the same basic design for all robots:
- 4 wheels with 1 Motor each,
- a metall (aluminium?) platform on which the arduino board, the battery pack, the motors and the wheels are mounted
1. all other components (sensors, an arm, the brush wheel, etc) can be decided on by each team. They come with their own mounting devices. These can then be secured on the main platform.
2. Each school provides all teams with the resources and skills it is good in. For LHB this would be making CAD with inventor and code writing with arduino. Gisle told me that metal work could easily be done in Lofoten. From Fuerteventura we all know that you are very good in 3D printing, TinkerCAD and coding. Some student from Kotka were very good in coding.

And here are our suggestions for our tasks in getting the robots build:
- the LHB students make 3D drawings for the basic robot model using inventor
- some other school decides on the wheels. They can be bought ready made or designed and build. They also decide how the wheels are fixed to the platform
- another school does the same process for the motors and battery pack.
- These three tasks should be completed by the middle of september
- after that the platform is build (Lofoten?) and each school is provided with the components for one basic robot model.
- If each international team has decided on their additonal components and how to build them they ask their respective team members to draw, build or print the components.
- To prepare for coding each international team should come up with a description about how their robot shall work (for example: shall the robot find the position of objects on the playground with sensors or shall it drive to set positions?, what shall the robot do when it finds an object?, how does it find its way back to the starting point?). This task should be completed by mid-october. Maybe its a good idea to break this tasks up into smaller sub-tasks. Please share your ideas.
- The teams should use Whatsapp as their main communication feature. As soon as they reach a decision about one of the sub-tasks they share their results on etwinning.

All the above is only a suggestion. Please don´t be shy to voice your comments, concerns and ideas to make it better.