**Participants of the SHORT-TERM EXCHANGES OF GROUPS OF PUPILS**

**Sustainable Tourism our way of living: Travel Green**

**ERASMUS+ KA2 GREEN ALLIANCE**

**CODE NUMBER: 2018-1-PL01-KA229-051018\_4**

**Torremolinos 16 – 20 february 2020**

In Torremolinos 20.02.2020

Coordinators meeting agreements in C5 in Torremolinos:

The date for the last mobility and final presentation of activities will take place in Cava de Tirreni in the following dates: May 17 arrival to 23 departure.

The final activities and responsibilities are as follows:

1. POLAND. Final tasks:

*LEGEND BOOK*: Poland is going to be responsible for the gathering, composition and printing of the Final Legend Book. It will be a digital product in eTwinning and 5 printed books, one for each participant, in an A4 in horizontal format with the project logo in the cover and the rest of Erasmus and schools’ logos. Each country will have a printed copy.

Each participant should prepare original drawings or images (not photos, but collage, paintings or drawings) made by the students, to illustrate their two legends. Each country has to prepare 3 trivial questios for each of their two legends, total of 6 per country.. These questions must be placed at the end of the legend book, as a final game.

The images and questions must be sent to Polish coordinator through etwinning in a Word (text) and JPGE (images) format The final date to send the images and the trivial questions to Polish coordinator is Friday April 17th.

1. SPAIN. For the final task:

*ENVIRONMENTAL WORDS DICTIONARY:* to be uploaded in etwinning. Please have all partners upload in word document with images included, as well as the presentations.

Poland, as coordinator, will check the budget for printing 5 copies, one for each participant. If possible, it will have the same A4 horizontal format and cover as the legend book.

1. RUMANIA . Final task:

*GREEN VIDEOS*: all the Green videos from the 5 participants must be gathered into 1 final video and uploaded it in etwinning.

1. TURKEY. Final task;

*GREEN ALLIANCE INTERNATIONAL WEB*. Update International Project Web linked to eTwinning, and the Green Alliance pages of each countrie’s web pages.

1. ITALY- Cava: Final Task:

*PHOTO EXHIBITION:*

 Italy will send by email the photo characteristics, dimensions and definition needed for printing with good quality the 5 photos per country.

The 5 photographs each country must send, are one of each of the following topics:

1. Natural landscape
2. Group photo.
3. Workshop photo
4. Cultural heritage
5. Fun Photo.

The 5 pictures of each country must show the different mobilities so it would be advisabli that every participant will focus in their own students and teachers reception in order to have diversity and representation of all schools and natural landscapes.

The final date to send the photos to Italian team coordination is Friday April 24th.

1. FINAL MEETING in Cava de Tirreni:

Student´s Presentations of final tasks of each country´s responsibility. Each country will present what they have worked on: Legend Book and play Green Monopoly Game in etwinning with the students (Poland),

Environmental Dictionary (Spain),

Green Videos (Romania),

International web page (Turkey),

and Cava`s PHOTO exhibition (Italy).

* All students will play Green Monopoly game digitally. Check if the trivial game is uploaded correctly on internet-etwinning.
* We can add fun and folklore activities students and teachers to this final meeting.
* Evaluation of the Project. Questionnaires
1. The place to gather all information is in Collaboration bewtween partners in eTwinning.
2. Cerro del Viento collaborative School on eTwinning, will be a part of our partnership with other Schools.
3. The final report it is estimated to be finished by 31 of August.

These are the resolutions that the Green Alliance Coordinators meeting agreed upon being the following participants,