**PLAN**

**eTwinning project “Young cooks”**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Month** | **Activity** | **Teachers** | **Students** | **Parents** | **Tool** |
| 14 – 20 January | We are … Presentation of the partners |  | Presenting all students together | Registration of parents wishing to participate in the project | Photos, videos, online platforms - of your choice |
| 21 - 27 January | Online training "Creative Teaching Approaches in Early Years" | Teachers from Bulgaria, Shumen will organize an online training for their colleagues |  |  | <http://zoom.com> |
| 21 - 27 January | Project Plan | Bulgaria, Shumen will organize discussion with teachers |  |  | <http://zoom.com> |
| 28 January –  3 February | Create a project logo, voting | Bulgaria, Tervel create poll for voting | Students prepare their suggestions and vote |  | Teachers of Tervel choose the way to vote |
| 4 – 10 February | Presentation of the traditional national cuisine of each partner. Each partner offers 1 recipe to be prepared by other participants | Teachers and students together choose traditional dishes typical of their country. Teachers and students together create 1 recipe | Teachers and students together choose traditional dishes typical of their country. Teachers and students together create 1 recipe | Suggestions from parents to present the national cuisine | Photos, videos in the TwinSpace. Recipes - pictures |
| 11 – 17 February | International day of cooking in each institution | Organizing appropriate environment and necessary products for cooking | They invite parents and students from other classes to taste the dishes | Cook with the students | Photos and videos in the TwinSpace |
|  |  |  | Tasting dishes and expressing their opinions about the dishes | They taste and express their opinions about the dishes | Video materials |
| 11 – 17 February | Searching for other culinary recipes included in the UNESCO list of the Intangible Cultural Heritage |  |  | They search for other culinary recipes and publish in the TwinSpace | TwinSpace |
| 18 -24 February | Create an online educational book | Georgia creates the book | They read the book | They read the book | <https://issuu.com/> or on another platform |
| 25 February – 3 March | Project evaluation | Create polls.  Bulgaria - Tervel creates a poll for parents. Bulgaria - Shumen creates a poll for teachers. Georgia creates a poll for students. Croatia summarizes the results | Fill an online poll | Fill an online poll | <https://www.google.com/drive/> |