ELECTRONIC CULTURAL PORTFOLIO of my REGION :
Projected timetable of activities
-P1 Other Project Events 09-2019
Project Management and Organization
Configure a communication platform (ex. Slack) for
good cooperation and communication between
partners during project implementation.
-P2 Other Project Events 09-2019
Project Management and Organization
All partners will select the project team (teachers,
students, administrative)
-P3 Other Project Events 10-2019
Project Management and Organization
Project team meetings
The local project teams will meet periodically in
order to plan, monitor and evaluate the activities of
the project
During the LTTAs (C1, C4) the coordinators will
have meetings.
-P4 Other Project Events 10-2019
Project Management and Organization
Planning the local activities
- Each project team will plan the local activities, and
the budget for it, in connection with project
objectives
-P5 Other Project Events 02-2020
Project Management and Organization
Evaluating the activities /project - questionnaires
will be distributed to students and teachers and
analyzed, after the LTTAs and at the end of each
school year
-P6 Other Project Events 11-2019 Project Management and Organization
Monitoring the project
-P7 Other Project Events 10-2019
Local activity
Documentation activity
Visiting a local magazine/newspaper publisher in
order to see the whole process and to understand
the roles in editorial/media teams
-P8 Other Project Events 11-2019
Local activity
Workshops
How to write an article?
How to carry out (empirical) research in order to
write an article?
-P9 Other Project Events 11-2019 Local activity
Documention of research topics
-P10 Other Project Events 11-2019 Local activity
Trips to cultural objectives for research
-P11 Other Project Events 11-2019
Local activity
Meetings with researchers, writers, press (media )
people for tips
-P12 Other Project Events 10-2019
Work meetings
Students and teachers will have regular meetings in
order to carry out the research and develop the ejournals
-P13 Other Project Events 09-2019
eTwinning space
Teacher and students will use eTwinning in order to
improve cooperation during the project
-P14 Other Project Events 10-2020 Local activity
Organizing an e-journalism club
in school
-P15 Other Project Events 11-2020
Local activity
Learning activity
How to reflect on my own learning process?
-P16 Other Project Events 11-2019
Dissemination and exploitation of project results
Dissemination meetings in partner schools – inform
students, teachers and parents about the project
and present the results
-P17 Other Project Events 12-2019
Dissemination and exploitation of project results
Dissemination meetings at the local level in order to
inform the local community about the project and
present the results
-P18 Other Project Events 10-2019
Dissemination and exploitation of project results
Designing, implementing and updating periodically
the website of the project
- linking the project web site with other web sites
(schools)
-periodical reports on progress (2 per year)
-discussions and exchanging examples of good
practice between partners via the communication
platform
-feedback from students on how the learning
process satisfies their needs to acquire the targeted
key competences
-P19 Other Project Events 01-2020
-P20 Other Project Events 02-2020
Dissemination and exploitation of project results
Disseminating the project during the international
and national meetings of partnership networks
-P21 Other Project Events 01-2020
Dissemination and exploitation of project results
Dissemination of the project at meetings initiated by
the National Agencies and competitions organized
by the NA

MOBILITIES

-C1 Short-term joint staff
training events 10-2019
 My cultural digital school
Dissemination and exploitation of project results
Promoting the project in mass media (articles,
interviews, video, etc.)

-C2 Short-term exchanges
of groups of pupils 02-2020
Culture and digital jurnalism

-C3 Short-term exchanges
of groups of pupils 05-2020
A picture is worth a thousand words

-C4 Short-term joint staff
training events 10-2020
Digital Journalism club

-C5 Short-term exchanges
of groups of pupils 02-2021
 Minorities culture

-C6 Short-term exchanges
of groups of pupils 05-2021
Presentation and assessment of the e-journals

COVID 19 measures taken after transnational meetings in August/ September 2020 and validated by national agencies :

The project will be extended (12 months, new ending date July 2022) (CF GANT chart)

Mobilities in 2019 and 2020 will have to be done online

C2 and C3 will be organized in spring 2021 by the Swedish partner and implemented through the use of Etwinning and different digital collaborative tools