ELECTRONIC CULTURAL PORTFOLIO OF MY REGION timetable of activities
ID	Activity Type	Starting / Period	Description
P1	Project Management and Organization	01.09.2019	Configure a communication platform for good cooperation and communication between partners during project implementation.
P2	Project Management and Organization	01.09.2019	All partners will select the project team (teachers, students, administrative)
P3	Project Management and Organization	10.09.2019	Project team meetings: / The local project teams will meet periodically in order to planning, monitoring and evaluating the activities of the project / During the LTTAs (C1, C4) the coordinators will have meetings.
P4	Project Management and Organization	10.09.2019	Planing the local activities / - each project team will plan the local activities, and the budget for it, in connection with project objectives
P5	Project Management and Organization	01.11.2019	Monitoring the project / -periodical reports on progress (2 per year) / -discussions and exchanging examples of good practice between partners via comunication platform / -feedback from students on how the learning process satisfies their needs to acquire the targeted key competences
P6	Project Management and Organization	15.02.2020	Evaluating the activities /project - questionnaires will be apply to students and teachers and analyzed, after a LTTAs and at the end of each school year
P7	Local activity / Documentation activity	01.10.2019	Visiting a local magazine/newspaper publisher in order to see all the process and to understand the roles in editorial/media team
P8	Local activity / Workshops	15.10.2019	How to write an article? / How to make a (an empirical) research in order to write an article?
P9	Local activity / Documentation	15.10.2019	Documenting on researches topic
P10	Local activity	20.10.2019	Trips to cultural objectives for research
P11	Local activity	20.10.2019	Meetings with researchers, writers, press (media ) people for tips
P12	Local activity / Work meetings	01.10.2019	Students and teacher will have regular meetings in order to carry out the researches and elaborate the e-journals
P13	eTwinning space	01.09.2019	Teacher and students will use eTwinning for a better cooperation during the project
P14	Local activity	15.10.2020	Organizing a e-journalism club in schools
P15	Local activity / Learning process	15.11.2020	How to reflect on my own learning process?
P16	Dissemination and exploitation of project results	01.11.2019	Dissemination meetings in partner schools – inform students, teachers and parents about the project and present the results
P17	Dissemination and exploitation of project results	01.12.2019	Dissemination meetings at local level in order to inform local comunity about the project and present the results
P18	Dissemination and exploitation of project results	01.10.2019	Designing, implementing and updating periodically the website of the project / - linking the project web site with other web sites (schools)
P19	Dissemination and exploitation of project results	15.01.2020	Promoting the project in mass media (articles, interviews, video, etc.)
P20	Dissemination and exploitation of project results	01.02.2020	Disseminating the project during the international / and national meetings of partnership networks
P21	Dissemination and exploitation of project results	15.01.2020	Dissemination of the project at meetings initiated by the National Agencies and competitions organized by the NA, ex. Erasmus Days

done
To be done at local level by all schools
Transformed into online activities

C2-C3-C5-C6 : Students exchange meetings will be transformed into online meetings in November 2021 and April 2022