## Arkusz 1
Timetable Erasmus Project 2018-1-PL01-KA229-050675_1 Oxford Style International Debates
ID | Activity type | Starting Period | Description
P1 | online conference | 09-2018 | We will conduct an online conference for teachers which aim is to share new information and ideas. At this point, we desire to work out a tool in form of a survey, which would measure level of skills and competence necessary to conduct high-quality debate. This tool will measure the initial level of students' competence as well as its increase after the project's ending.
C1 | Short-term joint staff training events | 12-2018 | Let's get started-Planning session. Meeting for teachers involved in he project. Poznan/Poland
P5 | survey | 12-2018 | At this stage, we would like to conduct an online survey among the candidates for the Oxford style debates. Survey will be conducted at the same time in all partner schools. All volunteers can take part in the initial survey, which aims at selecting a smaller group of participants. This type of test measures debating skills and will help as to compare the first stage results with the final results of debating competence. As a consequence, we would be able to estimate the increase in students' debating competence. Most of all, we want to focus on merit based argumentation skills, which exclude emotions and ad hoc decisions. When it comes to diagnosis of language skills increase, the survey will be attached by a debate language test which will be evaluated by English language teachers. The attached first test will be compared with the last, which will be conducted at the end of the project. The results will tell as how the language skills increased..
P3 | digital presentation | 02-2019 | Students will prepare a digital Presentation for broadcasting on social networks. At this stage, students will provide a description of the project with already taken actions like the previous online debates, their topics and results, presentation of the schools and teams. Each of the school will contribute with its own school/city/country presentation. As summary of the presentation, there will be a short quiz like Quizziz or Kahoot. As soon as the presentation is ready, it will be available in our eTwinning project, as well as the results of the quizzes...
P2 | motions for the debates | 03-2019 | At this stage, we expect to enlist a number of motions for the debates. Every participant can propos. a topic for the future debates. We will use eTwinning live event to exchange ideas for the first debate session. The proposals will be listed in Tricider Application. The event will be followed by voting in Tricider. ..
P4 | survay | 05-2019 | At this stage, we want to conduct a survey among students from all partner schools. The survey aims at collection of feedback. On the basis of the results, we want to improve our future debates. We believe that thanks to this evaluation the quality of our debates will rise. .
C2 | Short-term exchanges of groups of pupils | 05-2019 | Debate session 1- Alsfeld/ Germany
P7 | motions for the debates | 09-2019 | At this stage, we expect to enlist a number of motions for the debates. Every participant can propose. a topic for the future debates. We will use eTwinning live event to exchange ideas for the first debate session. The proposals will be listed in Tricider Application. The event will be followed by voting in Tricider. ..
C3 | Short-term exchanges of groups of pupils | 10-2019 | Debate session 2/ Vigevano / Italy
P8 | motions for the debates | 01-2020 | At this stage, we expect to enlist a number of motions for the debates. Every participant can propose. a topic for the future debates. We will use eTwinning live event to exchange ideas for the first debate session. The proposals will be listed in Tricider Application. The event will be followed by voting in Tricider. .....
C5 | Short-term exchanges of groups of pupils | 02-2020 | debate session 3 - Mafra / Portugal
P9 | motions | 03-2020 | At this stage, we expect to enlist a number of motions for the debates. Every participant can propose. a topic for the future debates. We will use eTwinning live event to exchange ideas for the first debate session. The proposals will be listed in Tricider Application. The event will be followed by voting in Tricider. .....
C4 | Short-term exchanges of groups of pupils | 04-2020 | debate session 4- Torrevieja / Spain
P6 | evaluation, dissemination | 05-2020 | Evaluation of the whole project: 1. We will conduct a final online survey for the participants concerning their debating skills. Its aim is to compare the results with the outcome of the initial survey. 2. The English skills of the participants in form of evaluation will be compared with the skills evaluation at the beginning of the project. 3. We want to conduct a quiz called Great Cultural Heritage Quiz. All participants will take part in the Quiz about all the participating countries and cities. Every partner school will prepare a part of the quiz concerning their countries.E