**MONTHLY REPORT**

|  |  |  |
| --- | --- | --- |
| 1. | Country | Estonia |
| 2. | Month/year | January 2016 |

**Activities**

|  |  |  |  |
| --- | --- | --- | --- |
|  | Activity description | Status(completed or not) | Upladed to e-twinning(yes/no) |
| 1. | Skype connections between project partners | no | no |
| 2. | Week of differences | yes | yes |
| 3. | Creating persona for first Persona Doll | yes | no |
| 4. | Developing Persona Dolls webpage | no |  |
| 5. | Project poster with logos from all institutions. | yes | yes |
| 6. | Finishing questionnaires for children | yes | no |

**Evaluation**

|  |  |  |
| --- | --- | --- |
| 1.  | Was everything done on time? | yes |
| 2. | Was there any problems with activities? | no |
| 3. | Assess activities progress and outcomes. | Everything was done as planned. Participated teachers from every group. |
| 4. | Improvements, if necessary. |  |
| 5.  | Evaluate cooperation between staff. | Very good. |
| 6. | Anything else to add. | no |