**MONTHLY REPORT**

|  |  |  |
| --- | --- | --- |
| 1. | Country | Spain |
| 2. | Month/year | December 2015 |

**Activities**

|  |  |  |  |
| --- | --- | --- | --- |
|  | Activity description | Status  (completed or not) | Upladed to e-twinning(yes/no) |
| 1. | Conducting questionnaire with children | Not completed |  |
| 2. | Report about Tallinn seminar to institutions webpage | completed | yes |
| 3. | Developing Good mate rules | completed | yes |
| 4. | Creating Good mate walls | completed | yes |
| 5. | Ordering Persona Dolls from South - Africa | Not completed |  |

**Evaluation**

|  |  |  |
| --- | --- | --- |
| 1. | Was everything done on time? | yes |
| 2. | Was there any problems with activities? | Teachers haven’t yet decided about dolls to be used in the Project. |
| 3. | Assess activities progress and outcomes. | Information meeting done. E-twinning page complete |
| 4. | Improvements, if necessary. | no |
| 5. | Evaluate cooperation between staff. | Very good |
| 6. | Anything else to add. | Luis Salvatella is a member in e-twinning Project.We have decided about teachers attendant meeting in Italy: Luis Salvatella and Mari Cruz Amate |