**MONTHLY REPORT**

|  |  |  |
| --- | --- | --- |
| 1. | Country | Estonia |
| 2. | Month/year | September 2017 |

**Activities**

|  |  |  |  |
| --- | --- | --- | --- |
|  | Activity description | Status  (completed or not) | Upladed to e-twinning  (yes/no) |
| 1. | New project year project team meeting | yes | no |
| 2. | Finnishing II differences book, printing out | yes | no |
| 3. | Creating profile for doll number 6 | no | no |
| 4. | Doll activities with children in classrooms | yes | no |
| 5. | Differences activity in classrooms, differences walls | no | no |
| 6. |  |  |  |

**Evaluation**

|  |  |  |
| --- | --- | --- |
| 1. | Was everything done on time? | no |
| 2. | Was there any problems with activities? | Some activities will be finished at the beginning of October, web version and printed out differences book is still at the printing studio waiting to be printed out. |
| 3. | Assess activities progress and outcomes. | Everything was done as planned. Some activities have needed more time because of long summer holiday. |
| 4. | Improvements, if necessary. | no |
| 5. | Evaluate cooperation between staff. | Very good |
| 6. | Anything else to add. | no |