**MONTHLY REPORT**

|  |  |  |
| --- | --- | --- |
| 1. | Country | CZECH REPUBLIC |
| 2. | Month/year | MARCH 2016 |

**Activities**

|  |  |  |  |
| --- | --- | --- | --- |
|  | Activity description | Status  (completed or not) | Upladed to e-twinning  (yes/no) |
| 1. | Seminar in Italy 12.03 – 18.03 | yes | yes |
| 2. | Summaries and presentations about the seminar in Italy | yes | yes |
| 3. | Doll activities with children | yes | yes |
| 4. | Project webpage | no | no |
| 5. | Skype meeting wit Italy | yes | yes |

**Evaluation**

|  |  |  |
| --- | --- | --- |
| 1. | Was everything done on time? | yes |
| 2. | Was there any problems with activities? | no |
| 3. | Assess activities progress and outcomes. | Doll profiles take more time then planned, there is some delay with some activities |
| 4. | Improvements, if necessary. | To work on the webside Persona Dolls on webside our kirdergarten |
| 5. | Evaluate cooperation between staff. | Very good |
| 6. | Anything else to add. | no |