**MONTHLY REPORT**

|  |  |  |
| --- | --- | --- |
| 1. | Country | GREECE |
| 2. | Month/year | October 2015 |

**Activities**

|  |  |  |  |
| --- | --- | --- | --- |
|  | Activity description | Status  (completed or not) | Upladed to e-twinning  (yes/no) |
| 1. | Introducing the project in partner’s institutions  Meeting with families | COMPLETED | NO |
| 2. | Creating the project team in partner institutions | COMPLETED | NO |
| 3. | Developing the form for the monthly reports with the coordinators | COMPLETED | YES |
| 4. | Activity of learning differences with the children: I’m special wall | STARTED | NO |
| 5. | Teaching differences | COMPLETED | NO |
| 6. | Establishing the work plan for the project in every partner institution; dividing the responsibilities and tasks | COMPLETED | NO |
| 7. | Creating the logo and poster for the project | NOT COMPLETED | NO |
| 8. | Creating the e-twinning page | COMPLETED | YES |
| 9. | Creating a project page on partner institution’s webpage; uploading the project activities | NOT STARTED | NO |
| 10. | Monthly report (September activities ) | NOT COMPLETED | NO |
| 11. | Uploading activities to the e-twinning page and to the institution’s webpage | NOT COMPLETED | NO |

**Evaluation**

|  |  |  |
| --- | --- | --- |
| 1. | Was everything done on time?  Some activities should be delayed | We started later than planned, because we didn’t have all the teachers working and no official news that we were accepted and sign the contract. |
| 2. | Were there any problems with activities? | Very slow start(see above) |
| 3. | Assess activities progress and outcomes. | Not |
| 4. | Improvements, if necessary. | Complete web page and e-twinning page |
| 5. | Evaluate cooperation between staff. | Teachers just started to be involved and cooperating in the project |
| 6. | Anything else to add. | Not |