***MINUTES – 3rd teachers’ online meeting***

***23/2/2020 4.30 pm CET time***

PARTICIPANTS:

Greece: Amalia Chompi

Turkey: Ozkan Akdugan

Portugal: José Antonio Carvalho

Catalonia/Spain: Marta Pey

1. COD-VID19: SITUATION IN EACH PARTNER COUNTRY

Schools are closed for the meantime and it is not clear when they will be open.

1. STEP 2: REVISION OF TASKS

We will try to make our students work from home, autonomously, on the tasks in STEP 2:

* 2.4. Political measures at local, regional and national level
* 2.5. UN Action Now Campaign

Ozkan will send detailed instructions on how students have to proceed to collaborate in [www.canva.com](http://www.canva.com) and [www.artsteps.com](http://www.artsteps.com) (step 3)

It was agreed that tasks in step 2 should be finished by the end of this school year, including the evaluation.

1. STEP 3:

It was agreed that these tasks will be done next school year, as we foresee lack of time to work with our students in this step.

Portugal, Turkey and Greece will be able to work with the same students. Catalan students will be new.

1. PROJECT WEBSITE:

Portugal will work on the project website and will add all teachers to be collaborators

1. DISSEMINATION ACTIVITIES:

All partners will compile dissemination activities done in each country and upload them in the corresponding page in the Twinspace.