Gantt\_July 2019

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Nr. | Activity | **W1**  **01-05** | **W2**  **08-12** | **W3**  **15-19** | **W4**  **22-26** | **W5**  **29-31** | Responsible |
| 1. | E-games- Each country will finalized a minimum 1 e-game on Bullying/ Digital  safe/ Cyberbullying/ Interculturality and other topics related to our project  objectives |  |  |  |  |  | All countries |
| 2. | Updating project web page |  |  |  |  |  | All countries |
| 3. | Final form of the Voice journal and receiving the ISSN for it |  |  |  |  |  | Romania |
| 4. | Dissemination activities  fate to face or/and by digital space |  |  |  |  |  | All countries |
| 5. | Renew the Dissemination Plan-changing the Objectives of Dissemination Plan |  |  |  |  |  | Italy and Greece |
| 6. | Renew The Risk Register |  |  |  |  |  | Romania |
| 7. | Updating materials on eTwinning page-COMPULSORY!!! |  |  |  |  |  | All countries |

Done by

Alina Gîmbuță, project coordinator

01.07.2019, Bistrița