Gantt\_October 2019

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Nr.  | Activity | **Week1****01-04** | **Week2****07-11** | **Week3****14-18** | **Week4****21-25** | **Week5****38-31** | Responsible |
| 1. | Second eTwinning event in each sending schools, after mobility in Italy/sharing good practices and dissemination. |   |  |  |  |  | All countries |
| 2. | Updating project web page |   |  |  |  |  | All countries |
| 3. | Dissemination activities fate to face or/and by digital space |  |  |  |  |  | All countries |
| 4.  | Flash-Mob in a public space (out-door or in-door), for marking theInternational Day of Non-Violence, on 20 October 2019. |  |  |  |  |  | All countries |
| 5. | Monitoring vulnerable students who are involvedin the project. |  |  |  |  |  | All countries |
| 6.  | First intermediate reports on dissemination, monitoring and impact(each country will send a national intermediate report with these 3 section/including monitoring of vulnerable students to the responsible countries). |  |  |  |  |  | Dissemination-Italy and GreeceImpact-CyprusMonitoring&Evaluation-Italy and Portugal- |
| 7.  | Uploading 3 intermediate reports on project webpage |  |  |  |  |  | Romania |
| 8.  | Starting steps for receiving e-Safety label at each school partners- athttp://www.esafetylabel.eu/ (European Schoolnet) |  |  |  |  |  |  |

Done by

Alina Gîmbuță, project coordinator

30.09.2019, Bistrița