## ToDoList
To Do List - KIDS ACTIVITIES | [5 empty] | © 2014 by Vertex42.com
Project: [KIDS - Keep Invest Donate Spend] | [5 empty] | To Do List Template
Project / Task | Status | Priority | Due Date | Evidências | Notes
Need Analysis Data - pupils, parents, teachers | In Progress | high | 22nd june 2015 | Basis for modules/workshops | Data in excel sheets
Modules guidelines | Planning | high | 10th July 2015 |  | Done by Turkey and Portugal
Modules contents for workshops | Planning | high | 1st September 2015 |  | Poland-teachers; Romania-pupils; Croatia-parents
Standard Activity Lesson Plan | Planning | high | 30th June 2015 |  | Poland and Croatia
Activities Lesson Plans | Planning | high | 23rd to 27th Sept 2015 |  | All partners according with schedule
Skype partners meeting | Approved | high | 6th July |  | 11:00 - Turkish time / 09:00 Portuguese time
Money box | Completed | - | 1 de Março 2015 | Photos from EB 2,3 exhibition in the library
Drama / Puppet show | In Progress | high | 2 de Junho de 2015 |  | To be recorded with English subtitles / Fantoches / atores tempo moderno
Financial Game Day | Completed | - | 22 de Março de 2015 | Photos from EB 2,3 exhibition in the library | Monopoly
' | Completed | - | 4 de Abril de 2015 | Photos | Grocery activity - 1st Cycle
' | Completed | - | 29 de Maio de 2015 |  | Shopping list: "More for less money" - Trabalho de grupo/€10 máximo produtos que podem comprar utilizando os folhetos
' | In Progress | high | 6 de Junho de 2015 |  | Monopoly / Portugal posponed 2nd round for Sept 2015
KIDS Fair + Donation to Crescer+ |  | low | Novembro de 2016 |  | Feira de Outono
History of Money - visita de estudo à Fundação Cupertino de Miranda - Paper Money Museum | Completed | - | 1 de Abril de 2015 | Photos from EB 2,3 exhibition in the library | Exposições nas escolas EB 2,3 de Marco de Canaveses e EB1/JI de Rua Direita
Planting trees |  | low | 22 de Abril de 2016
Visit to a local bank |  | low | 30 de Outubro de 2015
Exchange of Good Practices - chain activity | In Progress | high | 10 de Junho de 2015 | https://sway.com/oEw2BqSVj7cidli_ | Romania-Portugal-Turkey-Poland-Croacia
Pocket Money Diary |  | low | Setembro a Abril 2016 |  | 5th grade - Bankarro / 4th grade - Credit card
Visit to a supermarket |  | low | 25 de Setembro de 2015 |  | (6º ano Matemática)
Multiplier event |  | low | 04 a 08 de Abril 2016 |  | Kars, Turkey
3 days Workshops |  | low | November 2015 |  | 1- Pupils +brainstorm ? / 2- Teachers / 3- Parents + paintings
Wish Tree |  | low | 2nd/3rd weeks September 2015
Fairytale - chain story: Turkey-Croacia-Poland-Portugal-Romania |  | low | Jan to March 2016 |  | 500 words, 2 languages, drawings
Porfolios |  | low | 30 June 2016 |  | Each teacher does a portfolio with pupils work
Questionnaires | Completed | - | May 2015 |  | Organised and sent by Turkey
Mid-project evaluation | In Progress | high | March 2015 |  | Organised and sent by Turkey
2nd meeting - Portugal | Completed | - | 10th to 14th June 2015
3rd meeting - Croacia | Planning | high | 23rd to 27th Sept 2015
4th meeting - Romania |  | low | 3rd to 7th Fev 2016
5th meeting - Poland |  | low | 4th to 8th May
Project corner | In Progress | normal | 30 de Novembro 2014 | Photos from EB 2,3 exhibition in the library | Photos from EB1/JI Rua de Direita
Countries factsheets | Completed |  | 31 de Dezembro de 2014 | Photos from EB 2,3 exhibition in the library
Logo, Mascot, Poster | Completed |  | 31 de Dezembro de 2014 | Website + eTwinning
Project's brochure | Completed |  | 31 Outubro de 2014 | Brochure
Mascot 3D | Completed |  | Fevereiro de 2015 | Mascote

## Lists
Status | Priority | PICK
- | - | - | Edit these lists to change what shows up within the drop-down lists in the To Do List table.
Planning | high | Easy / Low Value
Pending Approval | normal | Easy / High Value
Approved | low | Hard / High Value
In Progress |  | Hard / Low Value
Pending Review
On Hold
Completed

## Help
HELP |  | © 2014 Vertex42.com
http://www.vertex42.com/ExcelTemplates/to-do-list-template.html
About
This to-do list was designed to be easy to customize. You can insert and delete columns as needed. To add more rows, just drag the table's drag handle in the lower right corner of the table.
Use the Lists worksheet to change what shows up in the drop-down lists in the Status, Priority, and PICK columns.
See the references below for more information about creating drop-down lists with data validation and named ranges.
Conditional Formatting
The Priority and Due Date columns use conditional formatting to highlight specific values. If you change the items in the Priority list, then you may need to edit the conditional formatting rule(s) as well.
In the ToDoList worksheet, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit the rules.
PICK
The PICK column can be used to help you indicate the Difficulty (easy or hard) and Payoff Value (low or high) for a particular task. You can delete this column if you don't want to use it.
See the PICK Chart page on Vertex42.com for more information about this method.
Terms of Use
This spreadsheet, including all worksheets and associated content is considered a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
See License Agreement
http://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this Help worksheet. If necessary, you may hide it by right-clicking on the Help tab and selecting Hide.
Additional Help
The link at the top of this worksheet will take you to the web page on vertex42.com that talks about this template.
REFERENCES
TIPS | Vertex42.com: Spreadsheet Tips Workbook
ARTICLE | Vertex42.com: PICK Chart
ARTICLE | Vertex42.com: Creating a Drop Down List via Data Validation
ARTICLE | Vertex42.com: Dynamic Named Ranges
Why this spreadsheet cannot be edited in Office for iPhone
- This worksheet uses the OFFSET function for dynamic named ranges
(work around: change the ranges to simple range references)
- Table formatting is not preserved, and you cannot edit values within Tables
(work around: convert the Tables to ranges)
- Conditional Formatting is not shown when viewing on the iPhone