|  |  |
| --- | --- |
| COUNTRY | **LITHUANIA** |
| MONTH/YEAR | **MAY-JUNE-2020** |

**We had to change the timeline due to Covid 19 and clases suspension. Some activities were adapted to the new situation**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **Activity description** | **Status(completed, in process/not com.)** | **Evidences** | **Uploaded to e-twinning (yes/no)** |
|  | **A-CHILDREN/TEACHERS/FAMILIES ACTIVITIES** |
| 1- | Chidren work with dolls at home. | Completed | Pictures and presentations | Yes |
| 2- | New activities: working at home | Completed | Pictures and presentations | Yes |
|  | **B- PROJECT TEAM ACTIVITES** |
| 1- | Monthly report on April activities | Completed | Document | Yes |
| 2- | Uploading activities to e-twinning page and every school webpages | Completed | Pictures, presentation, minutes | Yes |
|  | **C- INTERNATIONAL COORDINATION** |
| 1- | Proposal for activities to be done from home | In progress |  |  |

|  |  |  |
| --- | --- | --- |
| **PROBLEMS** | **IMPROVEMENTS** | **OTHERS** |
| The time lime has been changed and many of the activities that were planned for the months of May and June were delayed. Specially activities related with the end of the project: creation of final results, final evaluation, mobility tool, etc | National Agencies answered that we can continue with our Project during May and June we continued with adapted activities: working at home, an international book with récipes and planting seeds. | In September we will modify the time line and we will adapt the last part of the project to the new situation. |