## Feuil1
Etwinning project plan
Month | Week | Description
December | W51 | Write postcards and post it during holidays
| W52 | Holidays
January | W53 | Holidays
| W01 | GrA: Write the presentation of our Region, our school, our formation.
GrB: Creation of duets and attribution of transmissions to create + size limits (20cm x 20cm) + colors (black and white) + thickness 5mm
Crankrod system: Handle (Petelo) + Crank (Baptiste) + Piston (Julien) + Housing (Maxence) + Plexiglass
Cross of Malta system: Cross (Clément) + Wheel (Thomas) + Housing (Dylan) + Plexiglass
Belt and pulley system: Pulley1 (Tom) + Pulley2 (Mathys) + Housing (Dorian) + Plexiglass
Friction wheels system: Wheel1 (Corentin) + Wheel2 (Vincent) + Housing (Aurore+Logan) + Plexiglass
For each system, to make a illustrating sketch
Work to be done W02: each student of group B will have to find the vocabulary corresponding to his part
Italian groups 1, 2 and 3: working on their mechanical device "bevel gears box" step 1 gathering information and ideas - according the material uploaded on twinspace
| W02 | Inversion of groups
Italian groups 1, 2 and 3: sending a brief presentation on twinspace of their groups
| W03 | Selection of documents to upload on the Twinspace
Reading electronic messages sent by Italian students
Italian groups 1, 2 and 3: modeling on 3D cad Solidwoks their own device
| W04 | GrA: Work on action verbs and application through skit
GrB: Work on the technical vocabulary through pictures of systems to complete
Modelisation in 3D of different parts
Written summary of the session to upload on the Twinspace
Italian groups 1,2 and 3: uploading on etwinning their own device sketches
Meeting on eTwinning online between the two twinned classes to present themselves and the project so far
February | W05 | Inversion of groups
Italian groups 1, 2 and 3: assembly on 3D cad Solidwoks their own device
| W06 | GrA: Continuation of skits + Reading of documents upload by Italian students on the Twinspace
GrB: Work on the technical vocabulary through pictures of systems to complete
Modelisation in 3D of different parts
Written summary of the session to upload on the Twinspace
Italian groups 1, 2 and 3: prototyping their components
| W07 | Inversion of groups
Italian groups 1, 2 and 3: testing their prototyped components and check for improvements
| W08 | Holidays
March | W09 | Holidays
| W10 | GrA: Creation of vidéos who ask to 3 questions (What is it?, What is it for?, How does it work?)
GrB: Work on the technical vocabulary: To complete his workshops' lexical English-French
End of modelisation in 3D of different parts
Written summary of the session to upload on the Twinspace
Italian groups 1, 2 and 3: uploading on twinspace on their folder the Step and STL file for the twinned class
| W11 | Inversion of groups
Italian groups 1, 2 and 3: report about their own device in English for functioning and how to assemble it.
| W12 | To show videos to students and to upload on the Twinspace
| W13 | Internship
Italian groups 1, 2 and 3: preparing a presentation about their projects in English and Italian
April | W14 | Internship
Italian groups 1, 2 and 3: printing their device twice one for them one to sent to the twinned classe and assembling
| W15 | Internship
| W16 | Internship
| W17 | Holidays
May | W18 | Holidays
| W19 | GrA: Preparation online meeting
GrB: Printing parts and assembly of systems
Italian groups 1, 2 and 3: preparation for the meeting on line with French students
| W20 | Inversion of groups
Italian groups 1, 2 and 3: uploadind on eTwinning all the final design with STL file downloadable to be printed + completed with technical descrption and instructions to assemble
| W21 | Preparation of the package containing systems and to write short descriptions
Sending the package to Italian students
Italian groups 1, 2 and 3: uploadind on eTwinning all the final design with STL file downloadable to be printed + completed with technical descrption and instructions to assemble
Italian groups 1, 2 and 3: sending the package to French students
June | W22 | Receipt of the Italian package
Final online meeting
Italian groups 1, 2 and 3: Receipt of the French package + Final online meeting
W23
W24
W25
W26