## Slide 1: WATER AROUD US
Strategic Partnerships for school education
KA2 - Cooperation for innovation and the exchange of good practices
Isabel Castro
Financed by European Union
Jerez de la Frontera – Spain
18-23 May 2015

## Slide 2: Iceland Borganes – 8-14 November 2014

## Slide 3: First Report:
3 Years project:
  Start a 1 September 2014
  End a 31 August 2017
First report a 2 June 2016 reporting the activities done until 30 march 2016;

## Slide 4: General information:
We will receive the money in 3 parts. The fist will be 40% of the total budget;
We must send the first report until 2 June of 2016, reporting the activities done until 30 march 2016;
We must prove we spent 70% of the budget or the next payment will be reduced;
The report will be evaluate (max 100 points), and if it was not good, or late or we don’t execute all the activitiesof the project the school will need to send the budget received.
  If the punctuation will be 41-50 points the school must return to NA 25% of the budget received.
  If the punctuation will be 26-40 points the school must return to NA 50% of the budget received .
  If the punctuation will be 0-25 points the school must return to NA 75% of the budget received.
all the work done will be report in the MOBILITY TOOL and we will have formation provided from NA to do it.

## Slide 5: Any Information's about Mobility tool?

## Slide 6: All the activities produced must have:
The symbol of UE
The official logo

## Slide 7: Project: WATER AROUD US

## Slide 8: Common points that each school wishes to develop. The following issues were mentioned:
Increase the students intrinsic motivation for school activities;
Use of more innovative teaching/learning methods;
Improve the school results;
Improve the involvement of the students' families in schools;
Use of activities which complement academic curricula (offering a range of experiences that help students practice and develop work skills as well as explore creative thinking).

## Slide 9: Why the theme WATER?
It is a part of each partner school's study programme;
It is of vital significance for every organism on our planet;
It is a rich source for all kind of human utilization: inquisitiveness, exploitation, inspiration and creativity;
It is the perfect topic for an innovative and holistic pedagogical approach to improve teaching and learning;
It is a cross-curricular study theme;
Support the specific academic curriculum in subjects like:
  science
  languages
  technologies
  art
  music;
It offers a variety of subjects and experiments based on everyday situations that reinforce key competences and basic skills.
Encourage creative thinking in our students.
Improve teaching methods, strengthen our professional profile;
Involve parents
Involve associate partners in school activities.

## Slide 10: What we want to do:
first year:
  We plan to work on elementary scientific concepts connected with water (the properties of water in different subjects)
  Our focus will be on how partner schools teach properties of water by comparing their curricula and distinct teaching methods.
Second year
  We will continue the comparison work , an pluridisciplinary study about: water cycle;
  create a module with activities and methods to teach them in each partner school in order to and what we consider extended water knowledge:
    e.g. how human action influence the pollution of water
    what threats the decrease of potable water bring along,
    the second water cycle
    different ways of doing experiments with water
    etc.

## Slide 11: What we want to do:
3. Third year:
  Exploration of natural water supplies as: oceans, rivers, lakes and groundwater or underground water reservoirs, and even glaciers.
  Importance of water near our schools, what they have to offer in terms of:
    recreation,
    mental & physical health,
    sport
    tourism.
  Creation of a module.
  NOTE:
  Commemoration of the Water Day at 22 de Março in all three project years;
  With implementation of developed practices;
  Involving teachers and students, parents and associate partners.

## Slide 12: What we want to do:
Creating a Virtual Learning Platform e.g. eTwinning.
Doing a comparative analysis of the regular curriculum in all school partners of the theme WATER
Creation of innovative educational units (common modules).
Promotion of dissemination activities by:
  using the learning platform;
  publishing articles and reports in journals or newspapers;
  presentations/workshops/conferences for the teachers from our schools or other schools to share the project process and outcomes as examples of innovative practices;
Use open educational resources (OER) available for schools alongside with extensive implementation of information technology (ITC)

## Slide 13: Planed work for the first year:
First Year:
  A1 Introducing project at school and outside of school. Promotion through mass media. Communication, emails, Skype, Face Time on a regular basis. September 2014.
  A2 a project logo. October 2014. Germany Bergrheinfeld.
  A3 Virtual learning platform (eTwinning). October 2014. Germany Bergrheinfeld.
  A4 Website. December 2014. Germany Bergrheinfeld.
  A5 a lexicon of water-related words. January 2015. Finland. (Send words and definitions until middle of january )
  A6 Comparative analysis. February 2015. Iceland. Deadline end December 2014.
  A7 Educational unit about water properties. March 2015. Germany Werneck. Deadline end Jan 2015.
  A8 Calendar of creative and funny photos of water properties. April 2015. Latvia. Collecting 3 photos (ex 2560x1920 pixels format A4) deadline mid of October 2015 because of the late beginning of the project.
  A9 Evaluation. May 2015. Portugal. Deadline meeting in Spain.
  A10 Summing up activities writing reports. June 2015. Germany Werneck.

## Slide 14: Creation:
First Year:
  A1 Introducing project at school and outside of school. Promotion through mass media. Communication, emails, Skype, Face Time on a regular basis.
  A2 a project logo.
  A3 Virtual learning platform (eTwinning) .
  A4 Website.
  A5 a lexicon of water-related words,.
  A6 Comparative analysis.
  A7 Educational unit about water properties.
  A8 calendar of creative and funny photos of water properties
  A9 Evaluation
  A10 Summing up activities writing reports.
Second Year:
    A13 Booklet: Did you now facts about water (November 2015)
    A16 Poster about water cycle (April 2016)
    A17 Evaluation
Third Year:
  A21 Reference booklet: discover water near us, about interesting facts about water and water areas near us (Nov 2016)
  A23 video about Water near us (March 2017)
  …

## Slide 15: Monitoring the project:
The quality of the project's activities and results will be evaluated in different phases. For this end we will form a “Planning matrix for evaluation”.
This planning matrix for evaluation has four columns:
The first column: Expected Results of the project with concrete outcomes and products, which have been described earlier in this application in the section Description of the project.
The second column: Event or Collection Methods used with the concrete technique like questionnaires, quizzes or analyses.
The third column: Schedule and Frequency with details as to when the evaluation will be done and when it must be completed.
The fourth column: Quality assessment with a systematic rating in relation of how well we have succeeded in the given activity or result.

## Slide 16: Final evaluation:
For final evaluation we plan to evaluate the entire project at the end of each year with a questionnaire.
We wish to evaluate at least the following entities:
  project in each school,
  cooperation with partners,
  meetings,
  coordination process,
  final products.
This questionnaire will be fulfilled by the end of project year, and with its results we will prepare a final evaluation report.

## Slide 17: Finland Lappeenranta 8-14 November 2014

## Slide 18: First Year - Water properties
September 2014:
A1 Getting ready
- Participating students and teachers are informed on all details concerning the work plan, objectives and organized into teams. Introducing project to teachers, parents, wider educational systems, local administrative institutions; promoting through mass media. Communication (emails, Skype, Face Time) on a regular basis.
October 2014:
M1 Transnational Project Meeting in Iceland:
- First work meeting. Completing the logo competition, getting familiar with the virtual learning platform, brainstorming about Erasmus+ Corners and planning the creation of individual schools blogs and the existing project website as well as discussing the main activity namely the creation of an educational unit about water properties.
October 2014:
A2 Logo contest and setting up Erasmus+ Corners
- A competition on logo design in each school. Vote on the winners of each school to choose the ultimate project logo, which will be used throughout the project. Choosing a garment for all participants where we use logo as a print (a scarf, a cap, a T-shirt etc…)
November 2014:
A3 Virtual learning platform (eTwinning)
December 2014:
A4 Website
- As the Virtual Platform is a closed unity we use an existing website and school blogs to show and disseminate our work to wider audience.

## Slide 19: First Year - Water properties:
January 2015:
C1/C2 Learning Activity in Finland:
-Taking creative funny photos about water properties and working on A5 Lexicon about water. During the stay in Finland all guest students and teachers will be introduced to the wintery forms of water. Most activities will involve solid forms of water (snow and ice)
January 2015:
A5 Lexicon about water
- Lexicon will be a collection of entries in and their explanations in English on the theme water. Students and teachers work in groups to develop the entries, e.g. evaporation: ‘when water becomes a gas’. The lexicon will help learners to accomplish project tasks and activities in English,
February 2015:
A6 Comparative analyses of the regular curriculum in partner schools
March 2015:
A7 Educational unit about water properties
- It will contain innovative approaches collected from the best practises from all partner schools. This educational unit will also be easily downloadable from the platform for further use.
March 2015:
C3/C4 Learning Activity in Latvia: Commemorations of Water day and testing the educational unit about water properties
-Latvia has prior experience of organising Water Day activities in their school and they are willing to share their best practises in a concrete way by hosting a learning activity.

## Slide 20: First Year - Water properties:
April 2015:
A8 Putting together a Calendar of creative and funny photos of water properties
May 2015:
M2 Transnational Project Meeting in Spain with A9 Evaluation
A9 Evaluation of the first year’s project work
June/July 2015:
A10 Summing-up activities of the first project year (writing reports etc.)

## Slide 21: We are doing :
April 2015:
A8 Putting together a Calendar of creative and funny photos of water properties
May 2015:
M2 Transnational Project Meeting in Spain with A9 Evaluation
A9 Evaluation of the first year’s project work
June/July 2015:
A10 Summing-up activities of the first project year (writing reports etc.)

## Slide 22: Hosts for Transnational Project Meetings and Learning Activities Transnational Project Meeting= teachers only Learning Activities = teachers and students
Year | TPM October | LA Dec-Jan-Feb | LA Water Day | TPM May | Total
Year 1 2014-2015 | Iceland October 2014 (2 teachers) | Finland (end of January 2015) (2 teachers+3 students) | Latvia March 2015 (2 teachers+3 students) | Spain May 2015 (2 teachers) | 8 teachers 6 students
Year 2 2015-2016 | Germany B&W October 2015 (2 teachers) | Portugal Dez. 2015 (2 teachers+3 students) | Spain March 2016 (2 teachers+3 students) | Finland May 2016 (2 teachers) | 8 teachers 6 students
Year 3 2016-2017 | Latvia October 2016 (2 teachers) | Iceland Dez/Jan./Feb 2016 (2 teachers+3 students) | Germany B&W March 2017 (2 teachers+3 students) | Portugal May 2017 (2 teachers) | 8 teachers 6 students

## Slide 23: Certify of presence :
Officially it is necessary certify of presence in the visits with:
  Date (beginning and end)
  Name of the participant
  Objective of the activity and
  Total of working days

## Slide 24: Latvia Rujiena – 22-28 March 2015

## Slide 25: What we want to do:
Creating a Virtual Learning Platform e.g. eTwinning.
Doing a comparative analysis of the regular curriculum in all school partners of the theme WATER
Creation of innovative educational units (common modules).
Promotion of dissemination activities by:
  using the learning platform;
  publishing articles and reports in journals or newspapers;
  presentations/workshops/conferences for the teachers from our schools or other schools to share the project process and outcomes as examples of innovative practices;
Use open educational resources (OER) available for schools alongside with extensive implementation of information technology (ITC)

## Slide 26: Monitoring the project:
Monitoring is a form of evaluation or assessment, the outcomes (result) or impact evaluation,
  it takes place shortly after an intervention has begun (formative evaluation),
  throughout the course of an intervention (process evaluation) or
  midway through the intervention (mid-term evaluation).
Monitoring is not an end in itself. Monitoring allows to determine what is and is not working well, so that adjustments can be made along the way. It allows to assess what is actually happening versus what was planned.

## Slide 27: Monitoring the project:
The quality of the project's activities and results will be evaluated in different phases. For this end we will form a “Planning matrix for evaluation”.
This planning matrix for evaluation has four columns:
The first column: Expected Results of the project with concrete outcomes and products, which have been described earlier in this application in the section Description of the project.
The second column: Event or Collection Methods used with the concrete technique like questionnaires, quizzes or analyses.
The third column: Schedule and Frequency with details as to when the evaluation will be done and when it must be completed.
The fourth column: Quality assessment with a systematic rating in relation of how well we have succeeded in the given activity or result.

## Slide 28: Monitoring the project:
Expected results | Methodes used | Schedule and frequency | Quality assessment
With concrete outcomes and products | With a concrete technique like questionnaires, quizzes, analyses etc. | details as to when the evaluation will be done and when it must be completed | how well we have succeeded in the given activity or result.
A1 Introducing project at school and outside of school. Promotion through mass media: Communication, emails, Skype, Face Time on a regular basis. September 2014. | Observation Talking with partners Monitoring work performance and output (productivity) or Questionnaire?? |  | 

## Slide 29: Monitoring the project:
Expected results | Methodes used | Schedule and frequency | Quality assessment
A2 a project logo. October 2014. Germany Bergrheinfeld. |  |  | 
A3 Virtual learning platform (eTwinning). October 2014. Germany Bergrheinfeld. |  |  | 
A4 Website. December 2014. Germany Bergrheinfeld. |  |  | 

## Slide 30: Monitoring the project:
Expected results | Methodes used | Schedule and frequency | Quality assessment
A5 a lexicon of water-related words. January 2015. Finland. (Send words and definitions until middle of January ) |  |  | 
A6 Comparative analysis. February 2015. Iceland. Deadline end December 2014. |  |  | 

## Slide 31: Monitoring the project:
Expected results | Methodes used | Schedule and frequency | Quality assessment
A7 Educational unit about water properties. March 2015. Germany Werneck. Deadline end Jan 2015. |  |  | 
A8 Calendar of creative and funny photos of water properties. April 2015. Latvia. Collecting 3 photos (ex 2560x1920 pixels format A4) deadline mid of October 2015 because of the late beginning of the project. |  |  | 

## Slide 32: Planed work for the first year:
First Year:
  A1 Introducing project at school and outside of school. Promotion through mass media. Communication, emails, Skype, Face Time on a regular basis. September 2014.
  A2 a project logo. October 2014. Germany Bergrheinfeld.
  A3 Virtual learning platform (eTwinning). October 2014. Germany Bergrheinfeld.
  A4 Website. December 2014. Germany Bergrheinfeld.
  A5 a lexicon of water-related words. January 2015. Finland. (Send words and definitions until middle of January )
  A6 Comparative analysis. February 2015. Iceland. Deadline end December 2014.
  A7 Educational unit about water properties. March 2015. Germany Werneck. Deadline end Jan 2015.
  A8 Calendar of creative and funny photos of water properties. April 2015. Latvia. Collecting 3 photos (ex 2560x1920 pixels format A4) deadline mid of October 2015 because of the late beginning of the project.
  A9 Evaluation. May 2015. Portugal. Deadline meeting in Spain.
  A10 Summing up activities writing reports. June 2015. Germany Werneck.

## Slide 33: Publicity

## Slide 34: Spain Jerez de la Frontera 18-23 April 2015

## Slide 35: Monitoring the work done

## Slide 36: Planed work for the first year:
First Year:
  A1 Introducing project at school and outside of school. Promotion through mass media. Communication, emails, Skype, Face Time on a regular basis. September 2014.
  A2 a project logo. October 2014. Germany Bergrheinfeld.
  A3 Virtual learning platform (eTwinning). October 2014. Germany Bergrheinfeld.
  A4 Website. December 2014. Germany Bergrheinfeld.
  A5 a lexicon of water-related words. January 2015. Finland. (Send words and definitions until middle of january )
  A6 Comparative analysis. February 2015. Iceland. Deadline end December 2014.
  A7 Educational unit about water properties. March 2015. Germany Werneck. Deadline end Jan 2015.
  A8 Calendar of creative and funny photos of water properties. April 2015. Latvia. Collecting 3 photos (ex 2560x1920 pixels format A4) deadline mid of October 2015 because of the late beginning of the project.
  A9 Evaluation. May 2015. Portugal. Deadline meeting in Spain.
  A10 Summing up activities writing reports. June 2015. Germany Werneck.

## Slide 37: Monitorization of the project:
Planed Work | Date | End produt Cordinator | Monitorization
A1 - Introducing project at school and outside of school | September 2014 |  | Done
A2 - Project logo contest | October 2014 | Germany Bergrheinfeld | Done
A3 Virtual learning platform (eTwinning) | December 2014 | Germany Bergrheinfeld | Needs some improvements
A4 Website | December 2014 | Germany Bergrheinfeld | Needs some improvements
A5 a lexicon of water-related words | January 2015. | Finland | Done
A6 Comparative analysis | February 2015 | Iceland | 

## Slide 38: Monitorization of the project:
Planed Work | Date | End produt Cordinator | Monitorization
A7 - Educational unit about water properties | March 2015. | Germany Werneck | 
A8 - Calendar of creative and funny photos of water properties | April 2015. | Latvia | We change for the second year because the starting delay (comunication 29-9-2014) (Subvention came to Portugal in March)
A9 -Evaluation | May 2015 | Portugal. | 
A10 -Summing up activities writing reports | June 2015 | Germany Werneck | 

## Slide 39: A10 - Summing up activities writing reports. June 2015-Germany Werneck
All end product coordinators were already asked to send a short text of the process of producing the product in question (It easier to write the texts straight after we have done something);
  Finland sent a text about Lexicon WAU.
  Germany Bergrheinfeld - Logo/virtual learning platform /Website
  Iceland - Comparative analyses
  Germany Werneck – Educational unit
  Portugal – Evaluation: Questionnaire and report
  Germany Werneck – Summing up activities writing reports

## Slide 40: Hosts for Transnational Project Meetings and Learning Activities Transnational Project Meeting= teachers only Learning Activities = teachers and students
Year | TPM October | LA Dec-Jan-Feb | LA Water Day | TPM May | Total
Year 1 2014-2015 | Iceland 8-14 November 2014 (2 teachers) | Finland 8-14 February 2015 (2 teachers+3 students) | Latvia 22-27 March 2015 (2 teachers+3 students) | Spain 18-23 May 2015 (2 teachers) | 8 teachers 6 students
Year 2 2015-2016 | Germany B&W 5-9 (Monday-Friday) October 2015 (2 teachers) | Portugal ? Dez. 2015 (2 teachers+3 students) | Spain ? March 2016 (2teachers+3 students) | Finland ? May 2016 (2 teachers) | 8 teachers 6 students
Year 3 2016-2017 | Latvia ? October 2016 (2 teachers) | Germany B&W ? Dez/Jan./Feb 2016 (2 teachers+3 students) | Iceland ? March 2017 (2 teachers+3 students) | Portugal ? May 2017 (2 teachers) | 8 teachers 6 students

## Slide 41: Second Year: 2015-2016 What we planed to do:
Second year
  We will continue the comparison work , an pluridisciplinary study about: water cycle;
  create a module with activities and methods to teach them in each partner school in order to and what we consider extended water knowledge:
    e.g. how human action influence the pollution of water
    what threats the decrease of potable water bring along,
    the second water cycle
    different ways of doing experiments with water
    etc.

## Slide 42: Second Year: 2015-2016 What we planed to do:
September 2015:
  A11 Developing the Virtual learning platform
October 2015
  A12 Developing the Website
October 2015
  M3 5-9 October Transnational Project Meeting in Germany: Planning the second year’s work in detail
November 2015
  A13 Reference booklet: Did You Know? Facts about water
December 2015
  C5/C6 Learning Activity in Portugal:
  A14 Working on applications for android Mobil phones or tablets or similar about water cycle
January/February 2016
  A15 Educational unit about water cycle

## Slide 43: Second Year: 2015-2016 What we planed to do:
March 2016
  C7/C8 Learning Activity in Spain: Commemorations of Water day and testing the educational unit about water cycle and creating A16 Poster about water cycle
April 2016
  Finishing A16 the Poster about water cycle
May 2016
  M4 Transnational Project Meeting in Finland: Evaluation
May 2016
  A17 Evaluation
June/July 2016
  A18 Summing-up activities of the second project year

## Slide 44: Publicity

## Slide 45: Publicity – Spain (October 2014):

## Slide 46: Publicity – Spain (February 2015):

## Slide 47: Publicity – Spain (February 2015) (Presentacion ERASMUS)

## Slide 48: Publicity – Spain (March 2015):

## Slide 49: Publicity – Spain (14 April 2015):

## Slide 50: Publicity – Portugal – (Boletim da EA Valongo)

## Slide 51: Publicity – Portugal (School portal)

## Slide 52: Publicity – Portugal (School news paper – March 2015)

## Slide 53: Publicity – Germany

## Slide 54: Publicity – Germany (March 2015)

## Slide 55: Publicity – Germany (March 2015)

## Slide 56: Publicity – Iceland (February 2015)

## Slide 57: Publicity – Latvia (December 2014)

## Slide 58: Publicity – Latvia (February 2015)

## Slide 59: Publicity – Latvia (Scholl page during 2015)

## Slide 60: Publicity – Latvia (March 2015)

## Slide 61: Publicity – Finland (April 2015)

## Slide 62: Well done! We can be proud of our ERASMUS+ time!
Dear friends, We accomplish all our aims until now
2014-15
has a great ERASMUS+ work year I must say to all:

## Slide 63: END