Timetable of the implemented activities, outcomes  and products

Name of the project: Beyond Limits

Project duration: 09/2017 – 08/2020

TIMETABLE Girona Büren Ignalina

| Month | Activities (e.g. project management and implementation activities, local project work, class-room project work with learners, evaluation, mentoring, information and dissemination activities; virtual cooperation; transnational project meetings; transnational training, teaching and learning activities; production of intellectual outputs; multiplier events; …) Please number transnational training, teaching and learning activities (C1, C2,…), intellectual outputs (O1, O2,…) and multiplier events (E1, E2,…) in accordance with the application form. | Partners involved (e.g. all; DE, FR,IT; only universities; etc.) |
| --- | --- | --- |
| 9/2017 | Presentation of the project. Organising the working groups to distribute the project activities in the curriculum of the diferent subjects. Dissemination in the school’s websites. Evaluation questionnaries (status: before the project) | All the partners |
| 10/2017 | See: https://twinspace.etwinning.net/66307/pages/page/405994 24/10/17: meeting in Barcelona as a training activity with the organization SEPIE. Transnational meeting: Teachers project meeting in Büren to discuss the activities of the school year. “Market-Place” to define transnational working groups about “National Limits”; design of the working platform/blog; organisation of the logo-contest Exchange of best practice, dissemination of the information on the project in local press and school’s and local websites: Kick-off with balloon-competition and reception by the local administration in the townhall of Büren Start: Collection of the material about our town’s and school’s past, present. Start: presenting typical national sports (explainity-video-clip); creating challenges 24/10/17: meeting in Barcelona as a training activity with the organization SEPIE. | in Büren: All the partners (teachers) All the partners: History Department Sport department Instituto Sobrqués |
| 11/2017 | Tutorial Plan:”helping the others helping myself”, along the school year. (social and personal limits) Working in the Logos to participate in the LOGO contest, deadline 12/2017: Girona made the best Logos and brought 3 of them to Büren in 04/2018 | Institut Sobrequés All the partners Institut Sobrequés |
| 12/2017 | Music: planification of the song refering to social limits to be performed in Büren’s students’meeting. See: https://vimeo.com/419520690 The way to exile. Excursion to follow the road to exile after the Spanish civil war. Visit the Maternity of Elna, Argelers refugees camp. Excursion and display in the school See: https://agora.xtec.cat/inssobreques/batxillerat/sortida-al-museu-de-lexili-de-la-jonquera-mume-i-argelers/ getting over national limits: reasons and consequences of migration, local situation The after - school club “The school of young tourist guides”. (teachers and students) | All the partners_Music Teacher Institut Sobrequés Music teachers, History teacher Mauritius-Gymnasium_project-class Europe grade 7, 12 Ignalina Gymnasium |
| 1/2018 | First Art Exhibition at a Gallery (Fontana d’or) https://twinspace.etwinning.net/66307/materials/images The after - school club “The school of young tourist guides”. (teachers and students) A lecture of a professional guide about the peculiarities of a guide’s work (for students). Ending of the logo-contest: selecting the winner in 04/2018 in Büren | Institut Sobrequés_Specialist Ignalina Gymnasium Ignalina Gimnasium |
| 2/2018 | Sports challenge: basketball in wheel chair. Run by paraplegic people after an accident. Lecture and discussion after the activity. postposed to the 2nd project-year, see https://agora.xtec.cat/inssobreques/eso/basquet-en-cadira-de-rodes-2/ Sharing of good practice in “Aukštaitija“ National Park direction (for students). Excursion to Berlin: The fall of the wall 1989; students’ visit grade 9 (14 years); preparing the exposition for the C1 meeting in mai/2018 | Institut Sobrequés_MIFAS (Association of disabled people) Ignalina Gymnasium Mauritius-Gymnasium,_History and Politics teachers |
| 3/2018 | Questionnaire: yesterday_today_tomorrow: time machine See: https://twinspace.etwinning.net/66307/pages/page/420119/edit The competition of the best school guide. | All the partners Ignalina Gymnasium |
| 4/2018 | The trip to the Švenčionys herb factory. Students will learn how correctly to dry the herbs and to make healthy herb tea. Ecological footprints of students: collecting of the herbs for ecological tea (preparation for the second year of the project). | Ignalina Gymnasium |
| 5/2018 | C1 transnational training, teaching and learning activities; Project meeting with students (in Büren): “national limits” presenting the schools and towns (yesterday – today – tomorrow). Exposition about Berlin: historical example of getting beyond limits (outcome of Mauritius-students’ visit of Berlin ) sport challenges: triathlon-games (+wheel-chair – competition); Music workshop “beyond national limits”: Catalan song “When the town goes silent” + instruments Evaluation of the 1st part of the project. Lectures on the factors that cause climate change for students. Researches of the water and soil pollution in Ignalina region to find out what are the limits in nature when the process can not already be stopped. Recreational/ ecological trip to the mount Ažušilė (Ignalina region). | All the partners Ignalina Gymnasium |
| 6/2018 | Evaluation of the 1st part of the project in the schools. 1st Interim Report See: https://twinspace.etwinning.net/66307/pages/page/687262 Dissemination of the information on the project in local press and school’s websites. eTwinning project “Beyond Limits”: firste year page “beyond national limits” The survey/photosession „What is the further trip of the stuff gathered?” (all partner schools) Ecological trip for collecting the waste by the “Aukštaitija” National Park’s lakes. | Büren eTwinning-Team in the schools Ignalina Gymnasium |
| 7/2018 | Ecological footprints of students: collecting of the herbs for ecological tea. | Ignalina Gymnasium |
| 8/2018 | Ecological footprints of students: collecting of the herbs for ecological tea. | Ignalina Gymnasium |
| 9/2018 | Transnational meeting: https://twinspace.etwinning.net/66307/pages/page/694944 Teachers meeting: preparative meeting to fix up the details of the year, common program about “Natural limits” : climate change / renewable energy; presentation of the project: “Market-Place” to define transnational working groups about “Natural Limits”; Organizing the working groups (local and transnational).Sharing the experience of researches on water and soil pollution, photosession and ecological trip (Ignalina). Defining the sport challenges: “natural” sports exchange of best practice: tutorial system of learning (Girona), Sport program during school breaks to avoid aggressiveness and bullying (Girona), postposed to the next teachers’ meeting in Ignalina 09/2019: Green school-concept (Ignalina). Dissemination of the information on the project in local press, school’s and local websites. Presenting of the works planned in the meeting for the project work group (students and teachers) cancelled: The survey/ photo competition “ Waste sorting traditions in families” | in Girona: All the partners (teachers) All partner schools |
| 10/2018 | Green Schools club: organising the recycling in the classrooms and in the school. The selection of the photos from two photosessions for the photo gallery. Generalization of the survey results, possible solutions.Cancelled: Writing the articles for the digital journal ”European Geographics”.(Students); documentation of the project work in the Twinspace | Institut Sobrequés_ Green Schools club Mauritius-Gymnasium Students‘ speaker-team All the partners |
| 11/2018 | Green Schools club: making the boc 'n roll (reusable tissue wrappers for the sandwiches) to be given to the students with the logo and slogans. The leaflets „Where and how does the waste travel” The students are acquainted with the production of the ecological soap. | Institut Sobrequés_ Green S chools club Ignalina Gymnasium |
| 12/2018 | Working in transnational pairs about renewable energies in the technology class (Girona), biology and geography class (Büren), geography ( Ignalina). The production of the ecological soap.(students) Organising a photo gallery ”My green house” in the school. | Institut Sobrequés_Technology department, all partner schools Ignalina Gymnasium |
| 1/2019 | The survey of the ecological soap’s influence on the skin. The research of the school’s community about the ecological soap produced. | Ignalina Gymnasium |
| 2/2019 | The production of the packing for the herb tea and ecological soap from the recycled waste. Organising a trip of the photo gallery: “My green house” to other schools of Ignalina region. | Ignalina Gymnasium |
| 3/2019 | Music: planification of the song refering to natural limits to be performed in the meeting. https://vimeo.com/426959443 „circle of life“ Sports: Starting to present local natural sports (cancelled: explainity-video-clip); creating sport challenges: (t “natural” sports/sports linked with nature) Consolidation of the material picked and preparation for the conference on environmental issues „My green house“. | All the partners: Music teachers Institut Sobrequés Music department All the parters: sport teacher Ignalina Gymnasium |
| 4/2019 | Climate changes effects. Interviewing tourists and inhabitants about their awareness of sun effects on their skins and safety mesures. Giving advice. Conference on environmental issues ” My green house”(students and teachers) Dissemination of the information on the project in local press and school’s and local websites. 24/04/19: meeting in Madrid as a training activity with the organization SEPIE. JORNADA DE SEGUIMIENTO ASOCIACIONES ESCOLARES KA2019 | Girona, not: all the partners Ignalina Gymnasium Institut Sobrequés |
| 5/2019 | C2 transnational training, teaching and learning activities; Project meeting with students (in Girona): “natural limits” Exposition: my environment + your environment = how to protect our earth commonly Identify environmental problems ( climate change in the participating countries Methods/ technologies for solving these problem: Büren: windmills, deposit system for plastic bottles, charity project: collect bottles/deposit for a hospital in Sambia, seasonal and regional food: calender with recepies, collecting plastic waste in the “yellow bag”), Girona: solar cooking, skin protection against sun, instagram fotostudio “Save the world”, instruments made of waste; Ignalina: film “Soap production from herbs”, film “herbal tea”, tea tasting event, film “history of light in the developement stages of mankind”, reading nature with a natural alphabet, solar energy in Ignalina (pannel necessary to supply the Ignalina gymnasium with electricity), sport challenges: “natural” sports on the beach workshop music: Performance of “Cercle of life”, Ignalina: John Lennon’s IMAGINE reloaded Evaluation of the 2nd part of the project: natural limits Dissemination of the information on the project in local press and school’s and local websites. | in Girona: Institut Sobrequés + the partners: Students + teachers |
| 6/2019 | Evaluation of the 2nd part of the project in the school. 2nd Interim Report. new: eTwinning Project /Twinspace: pages “Beyond natural limits” documentation of the activities in all schools https://revistaldarull.blogspot.com/search/label/Erasmus%20Plus%20Beyond%20Limits And in Etwinning :https://twinspace.etwinning.net/66307/pages/page/420095 | All the ERASMUS teams involved Twinspace-Team in the schools Institut Sobrequés |
| 7/2019 | Project documentation on the school websites and in the twinspace | All the partners |
| 8/2019 | Project documentation on the school websites and in the twinspace | All the partners |
| 9/2019 | Transnational meeting: Teachers meeting: preparative meeting to fix up the details of the year, common program about “Personal limits” : films, books, persons that went “beyond limits”; presentation of the project: “Market-Place” to define transnational working groups about “Personal Limits”; Organizing the working groups (local and transnational). Defining the sport challenges: triathlon-games: “unusual sports”, cancelled: Domino-game (local + live while C3 final meeting) exchange of best practice: Individual tutorial system for students (Ignalina), DofE Challenges in Ignalina to enhance students’ self-consciousness and courage to go beyond their personal limits (Ignalina) | in Ignalina: All the partners (teachers) |
| 10/2019 | Sports: corporal exercises as a means for wellbeing and personal development (yoga and meditation, other personal experiences) ; extrem sports: human beings goint to they personal limits through sports; Working with different films about overcoming limits, like “On the way to school“, „La famille Bélier”, “I can dance” etc. | All the partners: sport teachers All the partners: language teachers, philosophy and religion teachers |
| 11/2019 | Working with different books about overcoming limits, like „Billy Eliot“, „Wonder”, “Origen Tambakunda”, “L‘esclau del Mercadal”, “Martin unter Druck”, “Tschick”... After reading the book the students did a film trailer emphasizing the efforts of the characters to overcome the limits. Invitaion of authors to come to school to talk about the books with our students. Non-traditional sport branches integrated into the lessons of Physical Education, like tennis in the dark. | All the partners: language teachers Institut Sobrequés Ignalina gymnasium |
| 12/2019 | Tutorial Plan:”helping the others helping myself”, along the school year. (social and personal limits) Art exhibition in Casa de Cultura in Girona: Beyond personal limits. See: https://agora.xtec.cat/inssobreques/batxillerat/exposicio-beyond-limits-personal/ cancelled: Short videos about non-traditional sport branches (prepared by students) | Institut Sobrequés Ignalina gymnasium Institut Sobrequés cancelled by all the partners |
| 1/2020 | Working about persons who went beyond their limits. Organising display in the school: wall of fame | All the partners |
| 2/2020 | MULTICAPACITIES: In the first year of High School with 16 year-old-students, a several lectures and talks were given by people who suffered different disabilities, included a school ex-teacher, who suffers multiple sclerosis. To show students that effort is important to overcome limits people may encounter throughout their lives, we organized poetry and music contests , lectures, and talks to exchange personal experiences and raise awareness of the problems these people have in their everyday life, like architectural barriers, for example. https://agora.xtec.cat/inssobreques/batxillerat/xerrades-multicapacitats/ WHEELCHAIR BASKETBALL : One of the most important activities with all 15 year-old-students was a meeting with people who after suffering an accident, are in wheelchair and practice sport. Sponsored by several NGOs, like Guttmann Institute, ONCE and MULTICAPACITIES, the students were invited to practice basketball in wheelchairs. See: https://revistaldarull.blogspot.com/search/label/Erasmus%20Plus%20Beyond%20Limits Social activity: the active week of overcomming personal limits (reading of the books in open areas at school, helping each other with the learning material , etc). | Institut Sobrequés Institut Sobrequés Ignalina gymnasium |
| 3/2020 | Music: planification of the song refering to personal limits to be performed in Ignalina’s meeting. See the video: https://vimeo.com/436468514 | Institut Sobrequés: Music Teachers |
| 4/2020 | Confinement: no normal school classes, distant learning via digital learning platforms no time left for project work | all the partners |
| 5/2020 | Starting an additional eTwinning project: Beyond Corona Limits https://twinspace.etwinning.net/114845/pages/page/954011/edit cancelled: C3 transnational training, teaching and learning activities; Project meeting with students (in Ignalina): “Personal limits” digital communication about the evaluation of the 3nd part of the project: natural limits Dissemination of the information on the project in local press and school’s and local websites. | All the partners: students and teachers |
| 6/2020 | documentation of results in the twinspace “Beyond personal limits” and “Beyond Corona Limits” preparing the final report (local parts in Ignalina and in Girona, final common report in Büren) | all the partners |
| 7/2020 | preapring the project exposition in Ignalina to be send to Büren | Ignalina Gymnasium |
| 8/2020 | no expositions at Mauritius-Gymnasium or in Büren’s townhall: Covid-19 restrictions for extern visitors | Ignalina Gymnasium |
| 09/ | Common final report in the Mobility Tool End of the project and of the eTwinnig projects “Beyond Limits” and “Beyond Corona Limits” | Mauritius-Gymnasium |