|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Activity****number** | **Title** | **Period** | **Description** | **Country** |
| **P1** | e-Twinning and Twinspace | Sep 2019- Aug 2021 | Set up e-Twinning site for the project for collaboration and sharing project work. Everybody to join and learn to add photos, films and documents. | Denmark All countries |
| **P2** | Project Presentation | Sep 2019-Aug 2021 | We will share the ACTIVE project with staff, pupils, parents, school boards and wider community through speeches, presentations, news in the websites etc.  | All countries |
| **P3** | Project Displays | Sep 2019-Aug 2021 | We will display the project and the schools/countries involved in all partner schools.  | All countries |
| **P33** | A Diploma for Learning/ Teaching/Training  | Sep 2019 | Denmark to design a diploma to use to recognize all participants in Learning/Teaching/Training Activities. The diploma will be given by the host school. | Denmark + all countries |
| **P7** | Children Baseline Survey | Sep 2019 | We will gather a baseline through Survey Monkey of the children´s understanding of how they learn. Denmark to produce a survey for the youngest. | England and Denmark + all countries |
| **P8**  | Staff Baseline Survey | Sep 2019 | We will gather a baseline of the staff´s understanding of how children learn. We will use SurveyMonkey. | England + all countries |
| **C1** | Staff Training Activity in Malta | Sep 28th-Oct 4th 2019 | Growth Mindset and eTwinningHost: Gozo College Secondary SchoolVictoria, Malta | Teachers:DK:3, UK:3, ICE:3, FIN:4, TUR: 3 |
| **P9** | Dissemination of the C1 | Oct-Nov 2019 | All schools to make plans how to include Growth Mindset to support ACTIVE learners. Ideas and activies shared through Twinspace/webpage. | All schools |
| **P4** | ACTIVE logo | Oct-Nov 2019 | Finland to design suggestions for the logo for the Erasmus+ ACTIVE. The best logo will be chosen during C2 in Finland. The logo will be used in all publications, websites, Twinspace etc. | Finland + all schools |
| **P5** | The Project Website | Oct 2019 | Malta to set up a project website. The website will showcase all aspects of our project and will be linked to websites in all partner schools. | Malta + all schools |
| **P10** | Believe in Yourself | Oct-Dec 2019 | Pupils to identify their strengths “This is what I´m good at”. Videos, cartoons, drawings etc. to be shared through Twinspace/website.  | All schools |
| **P6** | ACTIVE Project Song | Oct-Nov 2019 | Iceland to produce a project song. The song could be accompanied by actions for younger pupils. Partner countries to share videos their pupils singing project song. | Iceland + all schools |
| **P11** | GOAL setting | Nov2019 | PUPILS and STAFF to set goals for achievement for the end of the project in order to develop more resilience and perseverance. Goals are visible and photos are shared through Twinspace/webpage. | All schools |
| **P12** | GOAL keepers | Nov-Dec2019 | We will develop a buddy-system between schools for groups of children to support each other in reaching GOALS. We will create a GOAL KEEPERS FORUM in Twinspace/website. | All schools |
| **P13** | BRAIN BREAKS | Oct-Dec 2019(continues throughout the project) | Each partner school to develop minimum 5 Brain Break-activities and share with other schools to trial, video and feedback on the tasks. A Brain Break Bank will be added on the Twinspace/website. | All schools |
| **P14** | Learn Finnish in 5 minutes | Nov 2019 | Finland to prepare a short video for the visiting pupils to learn some Finnish (numbers, colours, introducing yourself - name,age,place). Share through Twinspace. | Finland + all schools to use |
| **C2** | Pupil Learning Activity in Finland | Nov 30th - Dec 6th2019  | ACTIVE Body and Mind in Varied Learning Environments.Host: Tehtaankadu Ala-asteen Koulu, Helsinki, Finland | Pupils and teachers:DK: 4+2Malta: 4+2UK: 4+4Turkey: 4+3Iceland: 4+2 |
| **P15** | Dissemination of C2 | Jan 2020 | Teachers and pupils to share what they experienced and learnt in Finland at their schools (assemblies, presentations - photos shared through Twinspace(webpage) | All schools |
| **P16** | ACTIVE Theme Days/Weeks | Feb 2020 - continues throughout the project | All schools support the pupils in the development of ACTIVE and independent learning. Opportunities for the pupils to co-construct their curriculum. Experiences shared through Twinspace/website. | All schools |
| **P17** | Learning Outside Classroom | March-Apr 2020 | Staff in all countries to implement training about how to incorporate more learning opportunities outside the classroom. Ideas and experiences shared through Twinspace/website | All schools |
| **C3** | Pupil Learning Activity in England | May 16th - May 22nd 2020 | Beaconing: Location Based ActivitiesHost: Howes Primary School in collaboration with Disruptive Media Learning Lab at Coventry University(Beaconing: Breaking Educational Barriers with Contextualised, Pervasive and Gamefull Learning) | Pupils and teachers:DK: 4+2Malta: 4+1Finland: 4+2Turkey: 4+2Iceland: 4+2 |
| **C4** | Staff Training Activity in England | May 16th-May 22nd2020 | Teacher Training in Active Learning - linked to Rhythm4Inclusion project by Coventry University.Host: Howes Primary School(Rhythm4Inclusion is part of University´s Erasmus+ Strategic Partnership “Promoting Social, Emotional and Learning Skills os Students with and without Special Education Needs by Developing Teachers Capabilities in Music, Dance and Digital Competences) | All partners send 2 teachers to this Staff Training Activity |
| **P18** | Dissemination of C3+C4 | June-Aug 2020 | All schools to arrange dissemination opportunities (presentations in classes, assemblies, school board etc) | All schools |
| **P19** | Application of ICT | Aug - Nov2020 | The pupils to create their own ICT trails for other pupils to test. These can be organized during theme days/weeks. Photos shared through Twinspace/webpage. | All schools |
| **P20** | ACTIVE MOVES! | Sep-Oct 2020 | Each school to practice lessons learnt during Staff Training (C4) in England. All partners will make a choreography for a piece of music chosen between the 3 pieces suggested by Turkey. Videos are shared through Twinspace/webpage. | Turkey + all schools |
| **P21** | Learn Icelandic in 5 minutes | Sep-Nov 2020 | Iceland to prepare a short video for the visiting pupils to learn some Icelandic (numbers, colours, introducing yourself - name,age,place). Share through Twinspace. | Iceland + all schools |
| **C5** | Pupil Learning Activity in Iceland | Nov 14th - Nov 20th2020(or 21-2th) | Healthy and ACTIVE body and mind: Coding, Robotics and MovingHost: Brekkuskóli in Akureyri, Iceland | Pupils and teachers:DK: 3+2Malta: 4+3Finland: 4+4Turkey: 3+2UK: 4+4 |
| **P22** | Christmas/New Year Greetings | Dec 2020 | Each country sharing a video with Christmas/New Year traditions, carols, ornaments, traditions. Twinspace. | All schools |
| **P23** | Dissemination of C5 | Jan 2021 | Dissemination of lessons learnt and experiences in Iceland though presentations in classes, assemblies etc. | All schools |
| **P24** | Use of robotics and coding | Jan-March 2021 | Each partner school to incorporate the use of robotics and coding within the curriculum. Each school will find the best suitable way to share this work and add photos of some of the lessons on Twinspace/webpage | All schools |
| **P25** | Learn Danish in 5 minutes | Jan-Feb 2021 | Denmark to prepare a short video for the visiting pupils to learn some Danish(numbers, colours, introducing yourself - name,age,place). Share through Twinspace. | Denmark + all schools |
| **C6** | Pupil Learning Activity in Denmark | March 20th-26th 2021 | Animated Learning and Outdoor LearningHost: Nordre Skole in DenmarkIn collaboration with Nature School, VIA University College and Animation workshop. | Pupils and teachers:Iceland 4+3Malta: 4+3Finland: 4+4Turkey: 4+2UK: 4+4 |
| **P26** | Dissemination of C6 | April-May 2021 | Dissemination of lessons learnt and experiences in Iceland though presentations in classes, assemblies etc. | All schools |
| **P27** | ACTIVE VIDEOS - lessons learnt | April 2021 | Each school to prepare videos, where pupils in all partner schools use ICT tools to share what they have learnt throughout the ACTIVE project. The videos will be used in the final Teacher Training Activity in Turkey. | All schools |
| **P28**  | Senior Leadership Activation | April-May 2021 | The coordinators in each partner school meet with Senior Leaders to discuss how the research and the findings of the project can be utilized to support the development of the curriculum. The output of this meeting is shared in Turkey. | All schools |
| **P29** | Pupils´End-of-Project-Survey | April-May 2021 | England to produce a SurveyMonkey questionnaire and each country to gather information of the impact of the project on pupils. | England + all schools |
| **P30** | Staff End-of-Project-survey | April-May 2021 | England to produce a SurveyMonkey questionnaire and each country to gather information of the impact of the project on staff. | England + all schools |
| **C7** | Staff Training Activity in Turkey | May 22nd-May 28t 2021 | ACTIVE sharing: Learning apps, evaluation tools and sustainabilityHost: Can Ibrahim Bodus Anadoli Lisesi, Turkey | Teachers:DK:3, UK:3, ICE:3, FIN:4, MALTA: 2 |
| **P31** | Showcase the ACTIVE project | May-Aug2021 | All partner schools will provide pupils and staff opportunities to showcase what they have learnt in course of the ACTIVE project. Photos of the events will be added in Twinspace. |  |
| **P32** | Final Report | Deadline:Aug 31st 2021 | The coordinator will gather all the necessary information from all partner schools to complete a final report on Mobility Tool and all partners fill any reports necessary to their Erasmus+ National Office.The coordinator will add project results in the Project Results Platform. The coordinator and the partners will apply for eTwinning certificate. | Denmark + all schools |