Erasmus+ ACTIVE online project coordination meeting

Date and time: September 22nd 2020

1. A brief update from each coordinator
* The situation at your school
* How are you keeping the project alive?
1. Learning & training activity in England
* November 2020 is not an option
* DK: we may alter the flight tickets by May 2021 against fee - can alter them ONLY for an exact date. If we declare the event force majeure, it can´t be arranged later in the project
* What to do?
1. Planned Learning/Training Activities
* Project period so far 1/9 2019 - 28/2 2022; we can ask for another 6 months (no funds)
* The earlier suggestion : DK LA in March-21, Iceland LA in Nov-21, Turkey LA Jan-22
* Is the plan realistic?
* Note: the flight prizes have sky rocketed
1. Virtual Mobilities?
* we can apply an Addendum to our Agreement
* we can use 15% of the Individual Support fund for the Activity
* The VirtMob to be documented with a Proof of Attendance specifying the name of the participant, length & purpose of the activity etc.
* Are VirtMob realistic to our project?
1. Project Activities
* We CAN continue with our project: sharing through Twinspace (courses?)
* We look at the plan and agree deadlines (revised plan attached)

ACCREDITATION

IF people are interested, we could briefly talk about Accreditation. We can also leave it for each country to decide, if they want to apply for it. In my earlier mail I wrote: “I would like you all consider applying for Erasmus accreditation. If you haven´t heard about it, please check it on the website of your NA. Accreditation will be important as the new Erasmus program 2021-27 has no similar possibilities for projects for schools as we have now. The "projects" will be of 1 year only and you can apply for 2 projects on the course of the program. With accreditation, you make an Erasmus plan for your school and when you want to do study trips/job shadowing/teacher training etc., you apply for the money.”

<https://ec.europa.eu/programmes/erasmus-plus/calls/2020-erasmus-accreditation?fbclid=IwAR2vdk54ho1WDr_dudIFklZJ2XB2OQ2iTjqVop8QHrk0X6fBcxEtyoLg_k8>