**DemEUcracy for ALL!**

Erasmus+ Strategic Partnership

2020-1-PT01-KA201-078358

|  |
| --- |
| **3rd Online Project Meeting** |
| **Date** | 14th April 2021 |
| **Time** | 7pm CET to 8pm CET |

|  |
| --- |
| **Participants** |
| Agrupamento de Escolas de Santo André Barreiro |
| Middelfart Gymnasium & HF |
| III Liceum Ogolnoksztalcace im. C.K.Norwida |
| Skola za ostecene sluhom-nagluve "Stefan Decanski"  |
| CollegeArchipelDesSaintes |

|  |
| --- |
| **Agenda** |
| 1 - Accomplishment of missing tasksLogotype competition – will be carried out in the following days.Website – French partner will finalize it by the end of the month.Students’ presentation – Serbian partner will post it within the next ten days. Dissemination – Erasmus + corners and social networks should be worked on. The Path to Freedom – Quizizz and Storybook – partners are working on it to finalize the ebook until the end of May. Danish partner will create a common Storyjumper ebook. Illustrations – the three best will be published by each country.2 - First Intermediate ReportPartners’ intermediate report will be sent to the project coordinator before the end of May.3 - Project’s Twinspace-Partners should try to have more interaction om Twinspace.The Danish partner will create a Forum for students to communicate.4 – First LTT Activity PortugalThe date for the first LTT in Portugal was settled. |