2nd transnational project meeting minutes

‘Learning beyond the classroom walls’

2016-1-UK01-KA219-024434

Date: 05-02-2018 to 08-02-2018

Venue: 137 SECONDARY SCHOOL ‘ANGEL KANCHEV’, SOFIA, BULGARIA

Participating partners:

- Withernsea Primary School, U.K.

- Kelmes „Kulverstuko” lopselis-darzelis, Lithuania

- Direzione Didattica Statale “Piazza Qualtro Novembre, Italy

- Ecole Communale d’Arquennes, Belgium

- Colegiul Tehnic Dimitrie LeonidaPetrosani, Romania

- CEIP Juan Garcia Perez, Tenerife, Spain

- 137 Secondary School ‘Angel Kanchev’, Bulgaria

Head of meeting: Claire Wright, project co-ordinator, UK.

Rositsa Dimova, host school project co-ordinator, Bulgaria.

Minute taker: Giancola Giuseppe

Table of contents

1.	Agenda	3

2.	Minutes	4

3.	Decisions	5

4.	List of participants	5

5.	Pictures	6

Agenda

2nd transnational project meeting

‘Learning beyond the classroom walls’

2016-1-UK01-KA219-024434

| Date: | 05-02-2018 to 08-02-2018 |
| --- | --- |
| Venue: | 137 SECONDARY SCHOOL “ANGEL KANCHEV”,SOFIA |

Work programme

| Tuesday 6th February |
| --- |
| Time 9.00 | to 9.15 | Arrival in Bulgaria – meeting information received. |
| Time 9.15 | to 10.30 | Discussion of the project so far - what has gone well and what could be improved for the second part of the project. Each partner to discuss what they have done in their school and also to discuss if more learning outdoors is taking place. Discussion – How can we measure the impact? Review partners' obligations, cooperation with each other and the importance of contribution to the project’s success. Read the application document highlighted and sent by co-ordinator before the meeting to use as discussion. |
| Time 10.30 | to 11.00 | Coffee break |
| Time 11.00 | to 12.00 | Go over dates for the rest of the project including training (Lithuania, Belgium and U.K.) and transnational meeting in Belgium. Look at travel options for these Outline training planned for other trainings to ensure the right staff are selected to attend |
| Time 12.00 | to 1.30 | Lunch |
| Time 1.15 | to 2.15 | Short tour of the school |
| Time 2.30 | to 4.00 | Go through activities still to do and set it out on a timescale |
| Time 4.00 | to 5.00 | Visit to the museum of Sofia |
|  |  | dinner |
| Wednesday 7th February |
| Time 8.45 | to 10.30 | Looking at expectations for the rest of the project including e-twinning; Looking at planning more chat sessions using Skype or eTwinning and doing some tests to improve these kind of tools; Planning interactive activities – pair up the partners |
| Time 10.30 | to 11.00 | Coffee Break |
| Time 11.00 | to 1.00 | Discussing dissemination of the project information using experience from Lithuania and Belgium so as to know what to expect Rewieving the Mobility tool. Discuss if everything is clear there and information is updated constantly. Each partner needs to make clear if they have made changes in the project compared to the application - Maybe someone took more participants than planned initially to trainings and partners' meetings. If so, how they were financed, etc. Partners present the prepared table of mobilities with detailed information and explanations (if needed) (attached template). |
| Time 1.00 | To 2.30 | Lunch |
| Time 2.30 | to 3.00 | Bulgaria Tenerife and U.K. to discuss pupil mobility and any first thoughts preferences to enable Bulgaria and U.K. to begin to prepare. |
|  |  | Dinner |

# Minutes

# The head teacher,  Vladimir Mikov, worked with partners on ice-breaking activities involving team building and working together.

# Each partner discussed what they had done in each school linked to the project aims and objectives. This included outdoor lessons, changes in outdoor learning provisions including new learning areas. All partners discussed the impact of the project on the curriculum and how it is changing the regular content following the last 2 trainings.

# The impact of the training was shared. We looked at questionnaires and compared results. Improvements of trainings were shown through the results, completed by every participant. There were no questions about these results.

# Training in Lithuania was discussed and dates of travel.

# Arrival in Vilnius Sunday 22nd April (by 4pm). A bus for travel will be arranged.

# Departure will be from Kelme Friday 27th to return to Vilnius

# Can book hotel in Vilnius

# Fights Saturday 28th

# Send details of participants to Irina (female/male)

# Training in Belgium was discussed and dates of travel.

# Arrival in Brussels (Brussels South is better but Brussels is possible too) 21st October

# Stay in Nivelles.

# Leave 27th October

# U.K. training will be in January 2019 – dates to be decided.

# Bulgara training will be in April 2019 – dates to be decided.

# Partners worked through the table of activities. Each activity was discussed (see table of activities)

# E-twining was looked at – where files were uploaded, new ict tools.

# Pino showed the use of Socrative – how to set up an interactive classroom.

# Dissemination was discussed. All partners were given a handout with the importance of this and ideas. Irina discussed from previous experience of Erasmus dissemination.

| countries | activities | time and… | responsibly |
| --- | --- | --- | --- |
| Italy - Bulgaria | Easter time Introduction How do you play Easter time? Show us your Easter symbols? Songs and rhymes related with Easter. Good bye and wishes | 1 min. – 2 children 5 min. – 2 children 5 min. – 2 children 5 min. – 2 children 1 min. - class | Rosa Palmieri Pavlinka Ivanova |
| Lithinia & UK | Singing easter somgs |  |  |
| UK & Romaina | Skipping games through progam |  |  |
| Spain & Belgium | Agreed between partners |  |  |

# Decisions

| No. | Decisions / Tasks | Deadline | Responsible person, institution |
| --- | --- | --- | --- |
| 1. | A short movie (3-5 minutes long) needs to be created by each partner school to show how the training from Tenerife has impacted the students. -can be recorded on any platform or programme. - Jose will collate the videos into one large video -The video must include an interview in mother tongue and translated into English. (could include how much the children have enjoyed the activities). - Mascots should also be included in the activities as it was stated in the original form. | By 15th March | -Send to Jose -The video of all schools will be shown at the next training meeting. A new page will be set up on etwinning linked to recycling so that ideas and projects can be posted including photographs. |
| 2. | Interim Report - Complete the interim report Partners should share any feedback given so that reports can be improved. | CHECK WITH YOUR OWN NATIONAL AGENCY | Submit it to your NA through Mobility Tool |
| 3. | Photographs and videos of the mascots- Continue to take photographs of the mascots – particularly of outdoor learning activities | Ongoing | Each partner to upload onto etwinning in the correct pages of the mascots. |
| 4. | Connect pupils through virtual mobility to share outdoor activities Partners linked by co-ordinator – Lithuania & U.K. (Kindergarten) Romania & U.K. Bulgaria & Italy Tenerife & Belgium Partners to discuss the focus for their linked lessons Both plan a game / song / skipping rhymes – practise and share together MORE DISCUSSION IN BULGARIA TM | May 2018 | All partners |
| 5. | Complete pupil questionnaire about countries and upload results | April 2018 | All partners |
| 6 | Prepare lesson plans for the activities done in your school – to include clear instructions/ pictures Prepare a word document of any outdoor activities completed due to this project – lessons etc. (IMPACT) In Maths , ICT, Games plan and science (recycling) | 31st May | E-mail documents to Claire to enable her to make up booklets/catalogues of outdoor activities as a resource to share in and beyond our schools. And on e-twinning |
| 7. | Training meeting in Lithuania Book travel | 22nd April – 28th April 2018 | All partners |
| 8. | Work with kindergarten children in own institution or another kindergarten following the training in Lithuania Details given in Lithunaia | By June 30th 2018 | All partners |
| 9 | Use group chat (skype, etwinning, hangout) for all partners for European laguage day. Activity decided... | 21st September | All partners |
| 9. | Travel day to Belgium Visit and work days Travel day Book travel | 21st October 2018 22nd – 26th October 27th October | All partners |
| 10. | Plan, teach and ‘record’ outdoor lesson with language as a focus following the training in Belgium Details given in Lithunaia | By 15th December 2018 | All partners |
| 11. | Travel to U.K. | To be decided | All partners |
| 12. | Travel to Bulgaria | To be decided | All partners |

# List of participants

# Meeting title

# The purpose of the activity: participation in the 2nd transnational project meeting

# Dates: 05-02-2018 to 08-02-2018

# Venue:

| No. | Name | Surname | E-mail | Address of participant | Position, Organization | Address of sending organization | Signature |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Claire | Wright | Toclaire.wright73@btinternet.com | Withernsea, UK | Withernsea Primary School, UK |  |  |
| 2. | Irina | Paradnikaitė-Abromavičienė | irinnai@yahoo.com | Taikos g. 53, Kelmė, Lithuania | Project manager, Kelmės „Kūlverstuko” l.-d. | A. Mackevičiaus g. 21, 86131 Kelmė, Lithuania |  |
| 3. | Milda | Alijošienė | milda4you@gmail.com | A. Mackevičiaus 25-45, 86129 Kelmė, Lithuania | Social pedagogue, Kelmės „Kūlverstuko” l.-d. | A. Mackevičiaus g. 21, 86131 Kelmė, Lithuania |  |
| 4. | Giuseppe | Giancola | giancola_pino@hotmail.com | Place Decamps 18, 7141 Carnieres Belgium | Ecole communale d Arquennes, Seneffe | Rue des Ecoles 10, 7181 Arquennes Belgium |  |
| 5. | Sandrine | Edart | sandrine.edart78@gmail.com | Rue de laRouge Croix 25/5 7180 Seneffe Belgium | Ecole communale d Arquennes, Seneffe | Rue des Ecoles 10, 7181 Arquennes Belgium |  |
| 6. | Rositsa | Dimova | r_dimova_137_sou@abv.bg | OK2, Sofia Bulgaria | 137 SU “Angel kanchev” | Bul. Europa 135, Sofia Bulgaria |  |
| 7. | Pavlinka | Ivanova | pavlinka.teacher@ | Lyulin, Sofia, Bulgaria | 137 SU “Angel Kanchev” |  |  |
| 8. | Stanislava | Nikiforova | sanikiforova@gmail.com | Lyulin, Sofia, Bulgaria | 137 SU “Angel Kanchev” |  |  |
| 9. | Irena | Raykova | irenarajkova@abv.bg | Lyulin, Sofia, Bulgaria | 137 SU “Angel Kanchev” |  |  |
| 10. | Rosa | Ramos Chinea | rosa_ramos_ch@hotmail.com | Tenerife, Spain | CEIP Juan García Pérez |  |  |
| 11. | Daura Isabel | Mendoza Baquero | dmenbaq@gmail.com | Tenerife, Spain | CEIP Juan García Pérez |  |  |
| 12. | Rosa | Palmieri | Rosa.palmieri2010@libero.it | San Nicandro Garganico, Italy | Direzione Didattica Statale Piazza Quattro Novembre |  |  |
| 13. | Rosalba | Marrocchella | rosalbamarrocchella@libero.it | San Nicandro Garganico, Italy | Direzione Didattica Statale Piazza Quattro Novembre |  |  |
| 14. | Grazia Lucia | Murano | grazialuciamurano@alice.it | San Nicandro Garganico, Italy | Direzione Didattica Statale Piazza Quattro Novembre |  |  |
| 15. | Gabriela Rodica | Rus | rus_gabriela@yahoo.com | Petrosani, Hunedoara, Romania | Colegiul Tehnic Dimitrie Leonida Petrosani | Petrosani, str. 22 Decembrie, nr. 6, Hunedoara, Romania |  |
| 16. | Mihaela | Manolea | miha2you@yahoo.com | Petrosani, Hunedoara, Romania | Colegiul Tehnic Dimitrie Leonida Petrosani | Petrosani, str. 22 Decembrie, nr. 6, Hunedoara, Romania |  |

# Representative from the receiving organisation: Vladimir Mikov, Head Teacher

Signature ________________________

# Pictures