**ERASMUS+ programme**

**Strategical school partnership (KA2)**

**OUR SCHOOL, OUR PLAYGROUND!**

 **Reference number: 2017-1-EL01-KA219-036230\_7**

**Evaluation and supervision plan at partnership level**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **no.** | **Evaluation fields** | **Required information** | **Information sources** | **Ways of information collecting** | **Organizing of the information collecting (by who, how, when)** | **Analysing procedures**  | **Interpretation Procedures and criteria** | **Reporting (whom, how, when)** |
| **1** | School Subjects’ Competences  | Required information for each of the studied school subject | Activity projects, games scenario, activities in images, activities video records, worksheets, students from the target groups  | Evaluation tests, group discussions, direct observation, questionnaires | **Who:** activities responsible teacher;**How:** applying of evaluation tests, group discussions,direct observation,questionnaires**When:** activities plan schedule  | Tests’ analysis,minutes of the group discussions, questionnaires’ analysis  | Progress charts, questionnaires’interpretation  | **Whom:** evaluation and supervision responsible,**How:** minutes, Progress charts, semestrial records**When:** trimestrial |
| **2.** | Project’s implementation | Amount of the project’s implementation, collaboration, cooperation, coordination of the projects’,activities’ acomplishment,  results’ achievement, students and teachers’motivation, social competences,project’s effect upon the school policy | Activities’ portfolios,Partner Teachers and team project’s teachers, students, the principal | School and partnership questionnaires | **Who:** evaluation and supervision responsible,**How:** questionnaires**When:** December 2017 May 2018 | Analysis of the documents and questionnaires | Minutes, questionnaires’interpretation  | **Whom:** project responsible,**How:** minutes, **When:** January 2018, June 2018 |
| Teachers from the project’s team | Activity records for each field of interest (project, evaluation,dissemination activities) | **Who:** project responsible,**How:** records’ checking:January 2018, June 2018 | Analysis of the records | minutes | School Departament of the Vaslui County -ISJ VASLUI January 2018, June 2018 |
| Project’s reponsibles | Intermediate record | National Agency,Record checking | Analysis of the records  | - | National Agency,July-August 2018 |
| **3.** | Transnational meetings (reunions) | Link between the aims of the event and the overarching aims of the transnational project/funding programme,Development of positive attitudes towards Europe | Reunion’s participants | Questionnaire, meeting record, participants’ list at reunion , certifications for attendance  | **Who:** evaluation and supervision responsible,**How:** applying questionnaires  | Analysis of the questionnaires, checking reunion’s documents | questionnaires’interpretation | Project responsible, minutes,participants’ list at reunion , certifications for attendance at each reunion  |

**Teacher, Mariana Munteanu, Romania**