**ERASMUS+ programme**

**Strategical school partnership (KA2)**

**OUR SCHOOL, OUR PLAYGROUND!**

**Reference number: 2017-1-EL01-KA219-036230\_7**

**Evaluation and supervision plan at partnership level**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **no.** | **Evaluation fields** | **Required information** | **Information sources** | **Ways of information collecting** | **Organizing of the information collecting (by who, how, when)** | **Analysing procedures** | **Interpretation Procedures and criteria** | **Reporting (whom, how, when)** |
| **1** | School Subjects’ Competences | Required information for each of the studied school subject | Activity projects, games scenario, activities in images, activities video records, worksheets,  students from the target groups | Evaluation tests,  group discussions, direct observation, questionnaires | **Who:** activities responsible teacher;  **How:** applying of evaluation tests,  group discussions,direct observation,questionnaires  **When:** activities plan schedule | Tests’ analysis,  minutes of the group discussions, questionnaires’ analysis | Progress charts, questionnaires’interpretation | **Whom:** evaluation and supervision responsible,  **How:**  minutes,  Progress charts, semestrial records  **When:** trimestrial |
| **2.** | Project’s implementation | Amount of the project’s implementation, collaboration, cooperation, coordination of the projects’,  activities’ acomplishment,  results’ achievement, students and teachers’motivation,  social competences,  project’s effect upon the school policy | Activities’ portfolios,  Partner Teachers and team project’s teachers, students, the principal | School and partnership questionnaires | **Who:** evaluation and supervision responsible,  **How:** questionnaires  **When:** December 2017  May 2018 | Analysis of the documents and questionnaires | Minutes, questionnaires’interpretation | **Whom:** project responsible,  **How:**  minutes,  **When:** January 2018, June 2018 |
| Teachers from the project’s team | Activity records for each field of interest (project, evaluation,  dissemination activities) | **Who:** project responsible,  **How:** records’ checking:  January 2018,  June 2018 | Analysis of the records | minutes | School Departament of the Vaslui County -ISJ VASLUI  January 2018, June 2018 |
| Project’s reponsibles | Intermediate record | National Agency,  Record checking | Analysis of the records | - | National Agency,  July-August 2018 |
| **3.** | Transnational meetings (reunions) | Link between the aims of the event and the overarching aims of the transnational project/funding programme,  Development of positive attitudes towards Europe | Reunion’s participants | Questionnaire,  meeting record, participants’ list at reunion , certifications for attendance | **Who:** evaluation and supervision responsible,  **How:** applying questionnaires | Analysis of the questionnaires, checking reunion’s documents | questionnaires’interpretation | Project responsible, minutes,  participants’ list at reunion , certifications for attendance at each reunion |

**Teacher, Mariana Munteanu, Romania**